Organisation of Eastern Caribbean States (OECS)

Skills and Innovation Project (SKIP) (P179210)

KNOWLEDGE TECHNOLOGY AND INNOVATION PLATFORM (KTIP)

OPERATIONAL ROADMAP

Version 1.1 | July 2026

Prepared for the Organisation of Eastern Caribbean States (OECS) Commission

Submitted by:

Dr. Marvin Pacheco

Table of Contents

Acronyms and Abbreviations	i

1	Background and Overview	1

2	Vision & Mission Alignment	4

2.1	Long Term Vision	4

2.2	Mission Statement	4

2.3	Guiding Design Principles	4

2.4	Key Success Criteria (3 – 5 Years)	5

3	Problem Statement & User Needs (Validated)	6

3.1	Key Ecosystem Challenges	6

3.2	Challenge-to-User-Need Mapping	7

3.3	Platform Features that Address Priority Pain Points	8

4	Stakeholder Ecosystem & Roles	9

4.1	Key Stakeholder Groups in the Innovation Ecosystem and Value Proposition	9

4.2	Governance and Accountability Principles	10

5	Platform Scope (Modules & Capabilities)	11

5.1	Core Platform Modules	11

6	Key User Journeys & Core Workflows based on Platform Roles	14

7	Operating Model & Governance	18

7.1	Platform Administration and Moderation	18

7.2	Verification and Approval Workflows	19

7.3	Platform Policies	20

7.4	Decision-making and Escalation Paths	21

7.4.1	Guiding Principles	22

7.4.2	Escalation, Complaints, Takedown and User Redress Process	23

7.4.3	Administrator Roles and Decision-Making Authority	23

7.4.4	Issue Classification Matrix	27

7.4.5	Special Procedures	30

7.4.6	Cross-Border and Multi-Jurisdiction Matters	31

7.4.7	Confidentiality of the Process	31

8	Intellectual Property Framework	31

8.1	Cross-Border Legal Context	32

8.2	Guiding Principles	33

8.3	Ownership Rules by Scenario	34

8.4	Co-Creation Safeguards by Scenario	37

8.5	Intellectual Property Protection Mechanisms	40

8.6	Terms of Use - IP-Related Obligations	42

9	Technical Readiness & Deployment Plan	45

9.1	Technology Stack and Architecture	45

9.1.1	Frontend	45

9.1.2	Backend	46

9.1.3	Infrastructure	46

9.2	Environments	46

9.3	Deployment and Release Process	47

9.4	Security, Compliance, and Monitoring	47

10	Priority Roadmap (Now / Next / After)	48

10.1	Now: Months 0–3 (Foundation & Launch Readiness)	48

10.2	Next: Months 3–6	49

10.3	After: Months 6–12	50

11	Quick Wins	50

12	Partnerships & Engagement Plan	52

12.1	Priority Strategic Partners	53

12.2	Planned Events, Challenges, and Campaigns	55

12.2.1	Launch and Platform Expansion Activities	55

12.2.2	Knowledge Exchange Activities	58

12.2.3	Innovation Inducement Activities	62

12.2.4	Other Innovation Initiatives	70

13	Risks & Mitigations	71

14	Success Metrics (KPIs) & Reporting	73

14.1	Project Appraisal Document (PAD) Evaluation Metrics (2030)	73

14.2	Community Growth	74

14.3	User Engagement	74

14.4	Platform Activity	75

14.5	Platform Health	76

14.6	Economic Impact	76

14.7	Other Project Metrics	77

14.8	Reporting Schedule	77

15	Sustainability Plan	78

15.1	Guiding Principles	79

15.2	Proposed Revenue Streams	79

List of Tables

Table 1: Key Success Criteria (3-5 Years)	5

Table 2: Challenge –to-User-Need Map	7

Table 3: Role and Value Proposition for Each User Group	9

Table 4: Governance Principles	10

Table 5: Accountability Mechanisms	11

Table 6: Core Platform Modules	11

Table 7: Verification and Approval Workflows	19

Table 8: Administrator Roles and Decision Making Authority	23

Table 9: Issue Classification Matrix	27

Table 10: Intellectual Property Ownership Rules on the KTIP	35

Table 11: Co-Creation Safeguards on the KTIP	38

Table 12: Intellectual Property Protection Mechanisms on the KTIP	40

Table 13: Intellectual Property Considerations for Terms of Use Agreement	43

Table 14: Environment Breakdown	47

Table 15: Foundation & Launch Readiness Activities	48

Table 16: Activation & Ecosystem Building Activities	49

Table 17: Scale	50

Table 18: Quick Wins for the Platform	51

Table 19: Partnership Engagement Plan	53

Table 20: Launch and Platform Expansion Activities	56

Table 21: KTIP Roadshow Expansion	57

Table 22: Caribbean Innovation Days Planning Activities	59

Table 23: Blue Economy Co-Creation Workshop Activities	60

Table 24: Sustainable Agriculture Co-Creation Workshop Activities	62

Table 25: OECS Super Regional Robotics Competition Activities	64

Table 26: Challenges & Call for Solutions - Sustainable Agriculture Activities	65

Table 27: Eco-Ventures Regional Innovation Challenge Partnership Activities	66

Table 28: KTIP Challenges & Call for Solutions - Sustainable Tourism Activities	67

Table 29: KTIP Innovation Hackathon – Online Activities	68

Table 30: KTIP Challenges & Call for Solutions - Blue Economy Activities	70

Table 31: Risks and Mitigation Activities	71

Table 32: Project Evaluation Metrics	74

Table 33: Community Growth Metrics	74

Table 34: User Engagement Metrics	75

Table 35: Platform Activity Metrics	75

Table 36: Platform Health Metrics	76

Table 37: Economic Impact Metrics	77

Table 38: Other Project Metrics	77

Table 39: Reporting Pulse	78

List of Figures

Figure 1: Escalation, Complaints, Takedown and User Redress Process	23

# Acronyms and Abbreviations

AUP	Acceptable Use Policy

CBU	Competitiveness Business Unit

CDB	Caribbean Development Bank

CERC	Contingent Emergency Response Component

ECRIA	Eastern Caribbean Robotics and Innovation Association

EU	European Union

GDPR	General Data Protection Regulation (GDPR)

GIZ	Gesellschaft für Internationale Zusammenarbeit

IDA	International Development Association

IDB	Inter-American Development Bank

IP	Intellectual Property

KTIP	Knowledge Technology and Innovation Platform

MOU	Memorandum of Understanding

NDA	Non-Disclosure Agreement

OECS	Organisation of Eastern Caribbean States

OECSC	Organisation of Eastern Caribbean States Commission

REP	Regional Enhancement Plans

RPIU	Regional Project Implementation Unit

RTST	Regional Technical Support Team

SDT	Software Development Team

SKIP	Skills and Innovation Project

TSIE	Technical Specialist Innovation and Entrepreneurship

# Background and Overview

The Organisation of Eastern Caribbean States (OECS) has initiated the Skills and Innovation Project to foster economic growth and development within the region.

The Project seeks to enhance post-secondary education and innovation investments among OECS Member States, promoting higher quality teaching and learning, generating more relevant education programmes, contributing to the regional innovation ecosystem, and better preparing students for the ever-changing world of work. It also aims to build human capital needed for countries to transition to lower-carbon economies by enhancing skills, fostering innovation, and engaging entrepreneurs in collaborative innovation.

The World Bank’s Board has approved US$36 million to Grenada, Saint Lucia, and the Organization of Eastern Caribbean States (OECS) Commission from the International Development Association (IDA) of the World Bank Group to finance the OECS Skills and Innovation Project. Each participating country will receive funding in the amount of US$15 million in credit, while the OECS Commission will receive an IDA grant in the amount of US$6 million.

The OECS Skills and Innovation Project will provide for investments in post-secondary education to promote transversal and advanced technical skills among youth while strengthening regional cooperation in post-secondary education. Over the next six years, the project will benefit forty thousand (40,000) youth, aged 18 to 34 years; who are currently or will enroll in post-secondary institutions in the OECS region. They will benefit from regional interventions to foster collaboration in the post-secondary education space. In addition, youth will benefit from the project’s provision of new tools to assess priority skills and support teachers. Additionally, one hundred and twenty (120) entrepreneurs and firms will benefit from grants to fund collaborative innovation projects. The project will also foster collaborative innovations within post-secondary institutions within OECS Member states.

The project consists of four components (C1 - C4) as follows:

- C1: Fostering regional collaboration for skills and innovation in the post-secondary space. Develop an overarching regional strategic framework for post-secondary education and design mechanisms to enhance collaboration among OECS Member States on post-secondary education, improve post-secondary data at the regional level, and develop a regional innovation ecosystem with strong participation of post-secondary institutions.

- C2: Strengthening post-secondary institutions and collaborative innovation. Provide direct support to National Colleges and other selected post-secondary institutions in participating countries to implement Regional Enhancement Plans (REPs), support collaborative innovation projects, and develop new or enhance existing programs to foster priority skills, to promote improved learning environments, enhanced skills development, and innovation in the OECS to respond to increasing private sector demand for skills.

- C3: Project Management and Technical Assistance. Provide technical assistance to support the implementation of Project activities and finance the establishment and functioning of three Project Implementation Units (PIUs), notably, (i) a PIU in the OECS Commission (OECSC) to procure regional activities for Component 1; and (ii) PIUs in Saint Lucia and Grenada to carry out activities under Component 2. Strengthen selected aspects of the OECS post-secondary education system’s performance, strengthen institutional capacity, and support project management.

- C4: Contingent Emergency Response Component (CERC). Facilitate the use of critical resources in the event of an eligible national emergency. It will have an initial zero budget allocation but would allow for rapid reallocation of project funds in the event of an eligible natural disaster or crisis that has caused or is likely to imminently cause major adverse economic and/or social impacts.

For the OECS Commission (OECSC), the Project is divided into two Components. Under Component 1, the OECS Commission (OECSC) will support the development of an overarching regional strategic framework for post-secondary education and of mechanisms to enhance collaboration among OECS Member States on post-secondary education, and the improvement of post-secondary data at the regional level. The OECSC will also support the development of a regional innovation ecosystem with strong participation of post-secondary institutions. Component 2, which will be implemented by Grenada and Saint Lucia at the national level, will provide direct support to post-secondary institutions to develop new or enhance existing programs for priority skills, and support collaborative innovation projects, to promote improved learning environments and foster better skills and innovation in the OECS to respond to increasing private sector demand for skills.

Component 1.2: Fostering regional innovation ecosystems with the participation of post-secondary institutions, benefits all OECS Member States by enhancing regional collaboration in post-secondary education and strengthening regional innovation ecosystems with private sector participation. The OECSC will be responsible for the following innovation and entrepreneurship-related activities under the OECS SKIP Project:

- Lead the creation and operationalization of the Knowledge Technology and Innovation Platform (KTIP). This would be a virtual platform to foster knowledge exchanges, networking, and collaboration in innovation activities in the Project’s prioritized sectors (e.g., sustainable agroindustry, blue economy, bioeconomy, circular economy, smart and sustainable tourism, renewable and clean energies, health sciences, and creative industries) for post-secondary education institutions, entrepreneurs, firms, the diaspora, and other key ecosystem actors.

The purpose of the platform will be to address the disconnect between the private sector and key players in the innovation ecosystem. It will also seek to address the information gaps, the lack of collaborative initiatives, and weak ecosystem linkages in general, which affect the youth labour market. The platform is also expected to foster discussions and collaborations on innovative solutions for mitigation, adaptation, and building resilience to climate change.

- Lead the organization of virtual and in-person activities to share knowledge and promote collaboration on innovation activities to generate momentum around innovation-led entrepreneurship.

The outcomes of these activities will integrate into and support the implementation of other Project components, including virtual knowledge exchanges for faculty and students at post-secondary education institutions and their connection to labour market opportunities. Once operational, the platform and activities will also be leveraged to identify potential innovation projects, collaborators, and investors for competitive grants for collaborative innovation to be implemented under the Project. Also, KTIP will be leveraged to establish a pool of recognized experts, practitioners, and scholars to be invited as evaluators and selectors of the project’s grant beneficiaries.

This document presents a comprehensive roadmap for the Knowledge Technology and Innovation Platform (KTIP) for the OECS Sub-Region. The KTIP is designed as a virtual hub that unites actors across the OECS innovation system, including students, entrepreneurs, researchers, mentors, investors, government agencies, and development partners, on a single, accessible digital infrastructure. This roadmap aims to capture key priorities, phased delivery plans, governance structures, risk mitigation strategies, and success metrics needed to operationalize the platform for the next twelve (12) months.

The roadmap draws on lessons learnt from comparable global innovation platform initiatives, including the EU's European Institute of Innovation and Technology (EIT) Knowledge and Innovation Communities, HYPE Innovation, and InnoCentive. Common challenges, such as low user adoption, inadequate governance, poor sustainability financing, and content stagnation are proactively addressed throughout this document.

# Vision & Mission Alignment

## Long Term Vision

The Knowledge, Technology, and Innovation Platform (KTIP) will become the go-to virtual space that catalyzes collaborations among actors in the innovation ecosystem by promoting knowledge sharing and co-creation of tailored regional solutions to achieve innovation-driven economic development.

## Mission Statement

KTIP's mission is to accelerate innovation-led economic growth across the OECS Sub-Region by connecting either necessity or opportunity with, knowledge, talent, and capital, to create a vibrant innovation ecosystem that collaborates, co-creates, and commercializes scalable solutions.

## Guiding Design Principles

- Inclusivity and Equity: The KTIP is designed for all OECS Member States. Multilingual support and zero-rating ensure wide participation from a broad range of stakeholder groups.

- Regional Ownership: The KTIP is developed, governed, hosted, and sustained by and for the OECS Sub-Region.

- Open Collaboration: Open project repositories, and community-moderated content promote free knowledge exchange while respecting intellectual property rights.

- Trust and Data Sovereignty: The platform is designed with robust security measures and data protection standards to safeguard user information, maintain trust, and ensure compliance with General Data Protection Regulation (GDPR) standards and other data protection regulations within the OECS. The platform architecture avoids vendor lock-in and prioritises interoperable solutions wherever feasible.

- Sustainability: The KTIP is designed with financial sustainability in mind to avoid dependency on any single donor or government funding cycle.

- Continuous Improvement: Platform features, content, and governance will be regularly reviewed with active users. User feedback loops and quarterly ecosystem assessments support iterative development The architecture is designed to accommodate future growth, additional functionalities, and evolving user needs while remaining adaptable to emerging technologies and innovation trends

- Accessibility: Platform features are designed for low-bandwidth, and screen-reader compatibility ensures the platform is accessible to users with disabilities and those with limited internet access.

- Integration: Platform is designed to integrate with existing systems, databases, and digital tools to maximize efficiency, reduce duplication, and enhance the user experience through seamless information sharing.

## Key Success Criteria (3 – 5 Years)

##### Table 1: Key Success Criteria (3-5 Years)

| Success Dimension | Success Criteria (by 2030) |
| --- | --- |
| User Reach | Active registered users from all 12 OECS Member States, with at least 200 verified firms/entrepreneurs |
| Economic Impact | At least 5 innovation projects tracked from ideation to early-stage revenue; EC$2M in cumulative financing facilitated through the platform |
| Ecosystem Density | 50+ mentor-mentee relationships active at any given time; 10+ collaborative innovative projects active at any given time; 10+ regional and international partners formally integrated |
| Knowledge Mobilisation | 50+ knowledge resources published and accessed; 10+ applied research partnerships between universities and private sector brokered via KTIP |
| Platform Health | Monthly active user rate of ≥40%; user satisfaction scores ≥4.0/5.0; platform uptime ≥99.5% |
| Financial Sustainability | Platform operating costs covered by blended revenue streams with no single source exceeding 40% of annual budget |
| Partnership Development | 10 active partners; two strategic partnerships established annually |
| Sustainable Governance and Operations | 99% system availability; support requests addressed within 48 hours |

# Problem Statement & User Needs (Validated)

## Key Ecosystem Challenges

- Fragmentation of Knowledge Networks: Innovation actors in the OECS operate in silos with no structured mechanism to discover potential collaborators or investors. Existing networks are informal, territorial, and difficult to access. Concerns over intellectual property theft and lack of trust remain a major limiting factor perpetuating this closed approach. Collaboration between the private sector and post-secondary institutions is limited and inconsistent hindering firms’ capacity to find the necessary skills and to strategically utilise the research and development services needed to maximize their innovation potential. Interactions typically include apprenticeships, internships, joint seminars, and part-time teaching roles, but do not include direct private sector contributions to curricula through research contracts or technology extension services. Joint initiatives like research projects, intellectual property initiatives, and publications are rare. Investment in building managerial and organizational capabilities and increasing firm capabilities through adoption and transfer of technology from universities, are crucial for emerging innovation ecosystems in the OECS. Creating mechanisms for direct technology transfer, including personnel rotations, can enhance alignment of knowledge supply and firm demand. This presents clear opportunities for innovation in the OECS.

- Limited Access to Risk Capital: Venture capital penetration in the OECS is extremely low. Entrepreneurs cannot easily match with investors, and investors cannot efficiently conduct due diligence on OECS startups.

- Talent Retention and Brain Drain: Young professionals trained in advanced skills frequently leave the region for employment elsewhere. A lack of qualified employees with the skills required for innovation, including transversal skills, is a major obstacle to innovation in the OECS, impeding productivity and economic growth. This obstacle is coupled with the perception that the market is too small for the cost of innovation. Generating in-demand skills through post-secondary institutions is a critical element to improve innovation in the OECS.

- Inadequate Support Infrastructure: Incubation and acceleration services are short term project-based initiatives that lack financial sustainability.

- Low Innovation Commercialisation Rate: Research institutions and universities in the region produce findings that rarely reach commercial application. Only 2.7 percent of firms in Grenada and 3.2 percent of firms in Saint Lucia have a department or group of professionals dedicated to research and development and only around 14 percent of firms in participating OECS countries report having introduced new or improved goods or services into the market.

- Digital Connectivity and Literacy Gaps: Significant connectivity costs and digital literacy gaps persist, particularly for older entrepreneurs and rural/remote populations.

- Donor Dependency and Sustainability Risk: Most existing innovation support programmes in the OECS are donor-funded and lack credible transition plans to self-sustaining models. Platform abandonment following funding cycles is commonplace.

## Challenge-to-User-Need Mapping

##### Table 2: Challenge –to-User-Need Map

| Challenge | Private Sector / SMEs | Students / Youth Innovators | Post-Secondary/Research Institutions | Mentors / Experts | Investors / Funders | OECS / Donors / Admins |
| --- | --- | --- | --- | --- | --- | --- |
| Fragmented networks | Cannot find innovation partners | Cannot find collaborators or mentors | Cannot find collaborative partners | Difficulty reaching mentees across islands and in the diaspora | No structured deal flow from region | Cannot monitor ecosystem activity |
| Limited capital access | Cannot access growth capital | No pathways to seed funding | Limited knowledge and access to grants | Cannot connect mentees to funders | No pipeline of vetted deals | Cannot track financing impact |
| Brain drain / talent flight | Cannot source local talent | No compelling reasons to stay | Weak pipeline of world class faculty and researchers | Hard to stay connected to region | Talent exits reduce returns | Hard to quantify retention |
| Weak support infrastructure | No R&D partnership pipeline | No structured programs | Research programs not prioritised | No framework for mentoring | No due diligence support | Hard to coordinate programs |
| Low commercialisation | Cannot access R&D outputs | Research ideas go unused | No pathway to commercialise research | No pathway to commercialise expertise | Hard to assess IP value | Cannot measure impact |
| Connectivity/literacy | Adoption barriers | Access barriers | Limited engagement | Engagement barriers | Trust barriers | Monitoring barriers |
| Sustainability risk | Uncertainty deters engagement | Programmes disappear | Reliant on subventions and Government funding | Investment of time wasted | Platform risk | Reporting gaps |

## Platform Features that Address Priority Pain Points

- Verified profiles and credibility: Trust is a critical barrier in regional ecosystems. A robust verification and endorsement system will be established.

- Intellectual property protection: Another key concern is the theft of intellectual property. A blockchain-based IP registry will be implemented and strong intellectual property policies will be clearly articulated and enforced.

- Discovery and matchmaking: Users will be able to find relevant collaborators, mentors, and opportunities quickly through the AI engine. This is a high-value feature that will drive initial adoption.

- Streamlined grant and funding discovery: Entrepreneurs and researchers will be able to discover, apply and track relevant funding through a frictionless interface.

- Clear onboarding with visible early value: New users must be able to identify value within their first session so a compelling onboarding experience will be crucial for early adoption.

- Centralizes information on regional events: Solution for coordinating events and stakeholder engagement activities via an event calendar, registration and hosting system

# Stakeholder Ecosystem & Roles

## Key Stakeholder Groups in the Innovation Ecosystem and Value Proposition

##### Table 3: Role and Value Proposition for Each User Group

| Stakeholder Group | Value Gained from KTIP | Primary Role on Platform |
| --- | --- | --- |
| Entrepreneurs & Startups | Talent matching, innovation partnership access, investor matching, funding opportunities, co-founder and team-building tools, mentorship, networking, | Project publishers, funding applicants, collaboration hosts |
| Private Sector / MSMEs | Innovation partnership access, R&D talent sourcing, challenge sponsorship, supplier discovery | Challenge sponsors, collaborative partners, resource providers |
| Students & Youth Innovators (18 - 35) | Access to mentors, training, funding opportunities, collaboration tools, and pathways to entrepreneurship | Project owners, project contributors, learners, hackathon participants |
| Researchers & Academics | Technology transfer pathways, industry collaboration, research dissemination, grant co-application | Knowledge contributors, research project leads, |
| Mentors & Expert Practitioners | Regional visibility, structured mentee access, contribution recognition, professional networking | Mentors, advisors, content contributors, challenge judges, |
| Investors (Investment Agencies, Angel, VC, Traditional Commercial and Development Banks) | Curated deal flow, due diligence support, portfolio monitoring, co-investment matchmaking | Investors, challenge sponsors, |
| Post-Secondary& Research Institutions | Industry linkages, research commercialisation support, grant discovery | Knowledge publishers, academic partners, event co-hosts |
| Government Ministries & Agencies | Policy intelligence, programme monitoring, ecosystem data, public-private partnership facilitation | Policy enablers, programme administrators, regulatory partners |
| OECS Commission | Regional integration data, programme delivery, member state equity, donor reporting | Platform governor, strategic partner, ecosystem facilitator |
| Development Partners & Donors (IDB, World Bank, GIZ EU, CDB) | Programme impact data, regional reach, co-investment matching, beneficiary reporting | Funders, challenge co-sponsors, technical partners |
| Diaspora Networks | Reconnection with home market, investment and mentorship pathways, remote work placement | Mentors, investors, challenge judges, talent connectors |

## Governance and Accountability Principles

##### Table 4: Governance Principles

| Governance Principle | Description |
| --- | --- |
| Regional Value | Decisions would support OECS-wide access, collaboration and data-informed planning. |
| Subsidiarity | Regional decisions will be taken only where coordination is necessary; National/institutional authority will be preserved where appropriate |
| Trust and safeguards | Priority will be given to the protection of privacy, confidentiality, integrity, accessibility and user redress. |
| Transparency | Emphasis will be placed on ensuring that users understand platform rules, responsibilities and avenues for support. |
| Sustainability | Governance will support long-term operation, adoption, maintenance and review. |

##### Table 5: Accountability Mechanisms

| Mechanism | Framework Application |
| --- | --- |
| Named Owners | Clear ownership for platform operations, data processes, guidance and issue handling. |
| Documented Decisions | Decisions, exceptions and unresolved matters are recorded and traceable. |
| Reporting Rhythm | Regular reporting on usage, incidents, data quality, complaints and changes. |
| Review Cycle | Governance rules are reviewed after launch and periodically updated. |
| User Redress | Users know how to raise concerns and what response standard applies. |

# Platform Scope (Modules & Capabilities)

## Core Platform Modules

##### Table 6: Core Platform Modules

| Module | Purpose | Priority |
| --- | --- | --- |
| 1. Identity & Profile Management | Verified user and organisational profiles with competency tagging, endorsements, and portfolio showcasing. Supports trust infrastructure across the platform. | Phase 1 (Core) |
| 2. Discovery & Matchmaking Engine | AI-assisted search and recommendation system that connects users to relevant collaborators, mentors, investors, and opportunities based on profile data, interests, and activity. | Phase 1 (Core) |
| 3. Projects & Collaboration Hub | Shared workspaces for innovation projects with task management, file sharing, milestone tracking, and co-authorship tools. | Phase 1 (Core) |
| 4. Funding & Grants Directory | Aggregated and searchable database of regional and international grants, loans, and equity instruments. Includes application tracking and eligibility matching. | Phase 1 (Core) |
| 5. Events & Programmes Calendar | Unified regional calendar for hackathons, bootcamps, investor forums, pitch competitions, webinars, and training events. | Phase 1 (Core) |
| 6. Knowledge Resource Library | Curated repository of research papers, toolkits, case studies, policy documents, and training materials relevant to OECS innovators. | Phase 1 (Core) |
| 7. Mentorship Programme Manager | Structured mentorship matching, scheduling, goal-setting, progress tracking, and feedback tools. Based on proven models from MicroMentor and iMentor. | Phase 1 (Core) |
| 8. Challenges & Open Innovation Engine | Host and participate in regional innovation challenges and problem-solving competitions with structured submission, evaluation, and prize distribution workflows. | Phase 1 (Core) |
| 9. Analytics & Impact Dashboard | Real-time ecosystem intelligence for platform administrators, OECS Commission, and development partners. Tracks engagement, impact, and funding flows. | Phase 1 (Core) |
| 10. Notification System | Real time push notifications and email notifications for user activities including messages and recommendations. | Phase 1 (Core) |
| 11. Badges and Gamification System | Badges for verified users, particularly investors and mentors. Achievement badges | Phase 1 (Core) |
| 12. Investor Deal Flow Portal | Private, verified environment for startups to present investment-ready profiles and for investors to conduct preliminary due diligence and express interest. | Phase 2 |
| 13. Learning Management System (LMS) Integration | Through the Virtual Campus, curated and partner-linked online courses, micro-credentials, and certification pathways supporting digital and innovation skills development. | Phase 2 |

| 14. Marketplace & Procurement Hub | Directory of regional innovation services, consultants, and suppliers. Supports public and private sector procurement of local innovative solutions. | Phase 3 |
| --- | --- | --- |

# Key User Journeys & Core Workflows based on Platform Roles

Entrepreneurs & Startups Journey

- Discovery: User discovers KTIP via social media campaign, KTIP roadshow, and other communication channels.

- Registration: Completes profile with key information user role, education, skills, sector interests/focus area and priority needs. Receives automated mentor and opportunity recommendations.

- Onboarding Value: Within first session, user finds at least one relevant event, grant opportunity, or mentor match. This 'first value moment' is critical to reducing churn.

- Engagement: Creates a project, applies for a grant, registers for a hackathon/challenge, and connects with a mentor or Private Sector / SME.

- Value Realisation: Secures mentorship, secures funding, enters an accelerator programme, attracts co-founder, all traced through the platform.

- Growth: Publishes project updates, earn recognition badges, builds a verifiable innovation portfolio.

- Capacity Building and Learning Journey: Users engage in structured learning pathways through e-learning modules, webinars, and workshops. These resources are designed to build entrepreneurial capacity.

Key friction points to address: Overly complex registration (limit to <3 minutes); no visible opportunities on first login (must display personalised recommendations immediately); lack of peer community (cohort-based onboarding with other users who registered in same period, leverage network effect and bandwagon effect).

Private Sector / MSME Journey

- Discovery: User discovers KTIP via direct engagement from KTIP team, social media campaign, KTIP roadshow, and other communication channels.

- Registration: MSME or corporate registers, describing sector, R&D interests, and procurement needs.

- Onboarding Value: Talent Discovery – Company representative browses student/young innovator and entrepreneur profiles to procure assistance with problems.

- Challenge Hosting: Creates or co-sponsors an open innovation challenge targeting a specific business or sector problem. KTIP provides challenge management tools.

- Value Realisation: Partnership Formation - identifies partners with relevant expertise. Initiates formal collaboration request via platform.

- Recognition: Challenges are promoted heavily on social platforms and OECS communication channels.

Key friction points to address: Challenges with finding talent and innovation partners (address via sending reminders to users to update personal information)

Student / Youth Innovator Journey

- Discovery: User discovers KTIP via post-secondary education partner, social media campaign, KTIP roadshow, and other communication channels.

- Registration: Completes profile with key information user role, education, skills, sector interests/focus area, and priority needs. Receives automated mentor and opportunity recommendations.

- Onboarding Value: Within first session, user finds at least one relevant event, grant opportunity, or mentor match. This 'first value moment' is critical to reducing churn.

- Engagement: Joins a project collaboration, applies for a grant, registers for a hackathon/challenge, or connects with a mentor.

- Value Realisation: Secures mentorship, secures funding, enters an accelerator programme, attracts co-founder, all traced through the platform.

- Growth: Publishes project updates, earn recognition badges, builds a verifiable innovation portfolio.

Key friction points to address: Overly complex registration (limit to <3 minutes); no visible opportunities on first login (must display personalised recommendations immediately); lack of peer community (cohort-based onboarding with other users who registered in same period, leverage network effect and bandwagon effect).

Faculty/Researcher Journey

- Discovery: User discovers KTIP via post-secondary education/research institution partner, social media campaign, KTIP roadshow, and other communication channels.

- Registration: Initiates registration using institutional email address. Selects 'Faculty / Researcher' as their primary role, builds profile and identifies areas of interest.

- Verification: System auto-verifies institutional email domain against a pre-loaded directory of OECS partner institutions. Profile receives a 'Verified' badge.

- Onboarding Value: Matching - platform suggests potential collaborators and funding opportunities based on research interest/focus area, access to knowledge resources.

- Engagement: Applies for funding, shares and accesses knowledge resources, identifies collaborators in the same field,

- Value Realisation: Receives research funding, co-creates new knowledge and products, and secures consulting opportunities.

- Recognition: Research activity is publicly visible on profile. Top faculty/researchers are featured in regional innovation communications on KTIP.

Key friction points to address: KTIP marketing defaults to entrepreneur-centric language; faculty feel the platform is 'not for them'. Ensure that the communication is inclusive. Faculty/Researcher cannot find industry partners open to academic collaboration. Include 'Collaboration Openness' field to all profiles with options: Research Co-Investigation, Knowledge Transfer, Curriculum Advisory, Consultancy, Not Currently Seeking.

Mentor Journey

- Discovery: User discovers KTIP via post-secondary education/research institution partner, social media campaign, KTIP roadshow, and other communication channels.

- Application: Expert applies to join as a verified mentor, submitting professional credentials and areas of expertise.

- Verification: System administrator reviews and approves mentor profile within two (2) business days. Profile receives a 'Verified Expert' badge.

- Onboarding Value: Matching - platform suggests relevant mentees based on sector interest/focus area and mentee needs.

- Engagement: Mentor accepts matches, schedules sessions through integrated calendar tool, sets goals, and logs session notes.

- Value Realisation: Mentee brings a project to market or improves competitiveness of an existing business.

- Recognition: Mentor activity is publicly visible on profile; endorsements from mentees enhance credibility. Top mentors are featured in regional innovation communications on KTIP.

Key friction points to address: Time burden of unstructured mentoring (address via structured 6-session programme format); no incentive to participate (address via professional recognition, speaking invitations and personal brand visibility).

Investor (Representatives from Investment funds/Grant Funding Agencies/Commercial Banks etc.) Journey

- Discovery: User discovers KTIP via direct engagement from KTIP team, social media campaign, KTIP roadshow, and other communication channels.

- Registration: Investor registers as a verified funder (individual angel, VC, or institutional investor). Provides investment thesis, sectors of interest, and ticket size range.

- Verification: System administrator reviews and approves investor profile within five (5) business days. Profile receives a 'Verified Investor' badge.

- Onboarding Value: Deal Discovery - Investor browses investment-ready profiles. Receives weekly curated digest of new projects matching thesis.

- Engagement: Expresses interest in a project; platform facilitates initial connection. Investor can view project milestones, team profiles, and uploaded project or pitch materials.

- Investment: Project status updated to “Funded”. Investment recorded (with consent) on KTIP for ecosystem metrics.

- Value Realisation: Investor receives return on investment

- Recognition: Investment is publicly visible on profile; endorsements from funding recipients enhance credibility. Top investments are featured in regional innovation communications on KTIP.

Key friction points to address: Challenges with vetting opportunities (address via due diligence support)

Open Assumptions and Dependencies

- Assumption 1: OECS Member States will support the platform through the regional focal points and co-promotion via existing digital government channels.

- Assumption 2: Post-Secondary Education and Research Institutions will encourage faculty, students and researchers to utilize KTIP.

- Assumption 3: Key stakeholders, including entrepreneurs, Business Support Organizations (BSOs), government agencies, development partners, and ecosystem actors and other private sector actors will play a key role in promoting the uptake of the KTIP by encouraging businesses at all levels to actively engage with and utilize the platform.

- Assumption 4: A clear IP framework is established before collaborative project tools go live to handle intellectual property created in collaborative project spaces on the KTIP.

- Assumption 5: It is assumed that data-sharing agreements and governance frameworks will be established and adhered to.

- Dependency: Promotion of investment deals require legal review to ensure compliance with Eastern Caribbean Securities Regulatory Commission (ECSRC) requirements for investment facilitation.

- Dependency: Mentorship programme quality depends on a cohort of verified mentors being onboarded early on. Mentor recruitment must be prioritised prior to launch.

- Dependency: Funding Availability and Continuity - The successful implementation of the platform is dependent on the timely availability and disbursement of adequate financial resources to support all phases of development and operation.

- Dependency: The implementation timeline depends on timely review and approval of key project documents, including technical specifications, procurement plans, and governance arrangements by Internal Technical Advisor and World Bank.

# Operating Model & Governance

## Platform Administration and Moderation

Administrative Roles and Responsibilities

- Regional Project Implementation Unit (RPIU): Overall accountability and oversight of all digital platforms under the SKIP project including KTIP. Receives quarterly reports; may direct a governance review of framework policy if there are perceived systemic issues based on data reported during the lifespan of the SKIP.

- KTIP Governance Committee: This will be a voluntary seven (7) member committee comprised of innovation ecosystem actors, duly constituted with a Terms of Reference and individual contracts for each member. The scope of work for this committee will be to make final independent decisions related to violations of platform policies and terms of use agreements and adjudicate on other governance and IP related matters as outlined in the TOR.

- OECS Competitiveness Business Unit (CBU): Overall accountability for KTIP platform strategy and stakeholder relations.

- Technical Specialist Innovation and Entrepreneurship: Oversight of platform strategy implementation, stakeholder relations, ecosystem metrics, KPI reporting, and impact evaluation.

- Technical Specialist EMIS and Virtual Campus: Technical oversight of platform operations, oversight of software development team, security, and feature development coordination.

- System Administrator: User verification, user engagement, content moderation, community programming, and first-line support.

- Regional Technical Support Team (RTST): Fourteen (14) distributed professionals across seven (7) Member States providing frontline support, capacity building, and participation in iterative development. This model embeds technical capacity within Member States rather than centralising it externally.

A critical lesson from comparable platforms is that understaffing the community management function leads to content stagnation and user disengagement. Community management must be treated as a core operational activity. The System Administrator will lead on this function and will be an essential resource for maintaining platform viability.

## Verification and Approval Workflows

##### Table 7: Verification and Approval Workflows

| Workflow | Process |
| --- | --- |
| New User Registration | Self-registration with email verification. Faculty/Researcher/Student accounts active immediately. Private Sector, Mentor, Investor, and Organisation profiles require manual review within 2-5 business days. Badges will be awarded upon verification. |
| Private Sector User Verification | System administrator verifies “Private Sector” accounts by confirming with company management that registered users are authorized to engage on the platform as a designated representative of the organisation. Will be allowed limited feature accessibility pending verification. |
| Mentor Verification | CV/LinkedIn review. Verified status renewed annually. |
| Investor Verification | Institutional Funding Agencies: System auto-verifies institutional email domain against a pre-loaded directory of OECS partner institutions. Non-Institutional/Unverified Investors: Proof of investment activity (previous deals or fund documentation). AML/KYC-lite check in line with ECSRC guidelines. Managed by Systems Administrator. |
| Faculty/Researcher/Student Verification | System auto-verifies institutional email domain against a pre-loaded directory of OECS partner institutions. |
| Organisation Verification | System Administrator will review legitimacy of the organisation based on digital footprint (e.g. website, social media, Google profile etc.) |
| Grant/Funding Listings | Verified by System Administrator against official funder websites before publication. Updated monthly. Expired opportunities auto-archived. |
| Content Publication | User-generated content (projects, resources) published with community reporting mechanism. Flagged content reviewed within 24 hours. Automated spam/harmful content filters in place. |
| Challenge Submission | Innovation challenge submissions reviewed against published criteria by designated evaluator panel. Blind review for equity assurance. |

## Platform Policies

There are three (3) critical policies meant to safeguard both the users and the operators of the platform from any damages and liability. These policies will form part of the overall Terms of Use Agreement and will be clearly articulated to the users in plain language on sign up. It should be noted that the terms of use agreement is a legally binding agreement between the platform operators and visitors, which covers areas such as acceptable use, intellectual property rights, liability limitations, account termination and governing law. The guiding policies are described below:

- Data Protection/Privacy Policy: Compliant with applicable data protection legislation in the OECS, and aligned to GDPR principles. Users retain ownership of their data and may request deletion at any time.

- Intellectual Property Policy: Content published on KTIP remains the property of the originating user/organisation. Collaborative project IP is governed by a published template Co-Creation Agreement/Model Contract.

- Acceptable Use Policy: Defines the standards for acceptable and prohibited behaviours of all users when using the platform. All users agree to AUP at registration.

These policies will be prepared, vetted and validated prior to launch of the platform.

## Decision-making and Escalation Paths

This section outlines how the KTIP receives, processes, and resolves all formal complaints, content reports, takedown requests, and redress applications from any person or entity affected by or interacting with the KTIP platform. It applies to all registered platform users, visitors, institutional partners, content contributors, mentors, investors, private sector members, university affiliates, and third parties whose content or interests may be affected by platform activity. The framework applies to the following categories of issue:

- Access Disputes: Denial of registration, account suspension, account deactivation, access restriction, or failure to access features to which a user is entitled.

- Data Correction and Privacy: Inaccurate personal data, unlawful data processing, data breach notification, right to erasure requests, and data portability requests.

- Intellectual Property (IP) Complaints: Claims of copyright infringement, trademark violation, patent misuse, or misappropriation of research outputs or creative works published on the platform.

- Confidentiality Breaches: Disclosure of information shared in confidence through KTIP project workspaces, mentoring sessions, grant co-application tools, or investor engagements.

- Safety and Harmful Content: Content or conduct that poses a risk of physical, psychological, financial, or reputational harm to an individual or group.

- Acceptable Use Policy (AUP) Violations: Harassment, hate speech, impersonation, spam, misinformation, or any other conduct prohibited by the KTIP Acceptable Use Policy.

- Contract and Agreement Compliance: Alleged violations of mentorship programme terms, challenge participation terms, partnership MOU, or organisational membership agreement.

- Moderation Disputes: Challenges to a content moderation decision made by the System Administrator, including content removal, warning issuance, or account restriction.

### Guiding Principles

- Fairness: Every person or entity submitting a complaint or subject to a complaint is entitled to a fair, impartial, and evidence-based process. No decision affecting a user's platform access or reputation is made without providing an opportunity for that user to respond.

- Proportionality: Responses are proportionate to the severity of the issue. Temporary content restriction is preferred over permanent removal where the facts remain under review. Account suspension is preferred over permanent deactivation unless the violation is severe and proven.

- Transparency: All parties are informed of the process stage, expected timelines, and the basis for any decision affecting them. Aggregate anonymised summaries of complaint volumes and outcomes are published in the monthly and quarterly platform progress report.

- Speed: Safety-critical matters are acted upon within hours. All complaints receive a substantive response within defined timelines. Unexplained delays are themselves a governance failure.

- Finality with Appeal: Every decision at Stage 5 is final at the OECS TSIE or CBU level unless appealed within the defined window. The appeal pathway will be clearly communicated in every Stage 5 decision notice. Decisions of the KTIP Governance Committee at Stage 6 are final within the platform governance framework.

- Non-Retaliation: No user who submits a complaint in good faith shall be subject to adverse action as a consequence of that complaint. Retaliation against a complainant is itself an Acceptable Use Policy (AUP) violation subject to this framework.

- Accessibility: The complaints and redress process is accessible to all OECS users regardless of territory, connectivity level, or technical proficiency. A non-digital complaint pathway (email to a published complaints address) is always available.

### Escalation, Complaints, Takedown and User Redress Process

The KTIP complaint and redress process follows a six-stage model. Every complaint passes through all six stages, though the time, resources, and decision authority engaged at each stage vary by issue classification. The six stages are outlined in Figure 1 below.

###### Figure 1: Escalation, Complaints, Takedown and User Redress Process

### Administrator Roles and Decision-Making Authority

The following roles are active participants in the escalation, ccomplaints, takedown and user redress process. Each role carries defined responsibilities, decision-making authority, and accountability. No role may exercise authority beyond that defined below.

##### Table 8: Administrator Roles and Decision Making Authority

| Role | Responsibilities in the Escalation Pathway | Decision-Making Authority | Accountability |
| --- | --- | --- | --- |
| System Administrator | First-line receipt of all complaints and reports; initial triage; temporary content actions; Acceptable Use Policy enforcement up to warning level; user communication at Stages 1–3; escalation to OECS TSIE | Can restrict content, issue warnings, suspend accounts up to 72 hours, and close low-priority complaints independently. Cannot permanently remove accounts or content. | Reports to OECS TSIE; decisions logged in complaint register reviewed weekly |
| Technical Specialist EMIS and Virtual Campus (or a designated SDT Representative) | Executes technical actions: content removal from servers, access restriction, evidence preservation, data correction, data deletion, account deactivation at request of System Administrator or OECS TSIE | No independent complaint decision authority. Executes decisions made by System Administrator or OECS TSIE within 24 hours of request. Confirms execution in writing. | Reports to RPIU; all technical actions logged with timestamp and instruction reference |
| OECS Technical Specialist Innovation and Entrepreneurship (TSIE) | Stage 4 review authority for all non-trivial matters; final Stage 5 decisions for most complaint categories; escalation to Competitiveness Business Unit for complex or high-stakes matters; quarterly reporting to RPIU | Can confirm content removal, reinstate content, issue final warnings, suspend accounts for up to 30 days, permanently restrict features, permanently deactivate accounts (subject to KTIP Governance Committee notification), and close all complaint categories except those requiring KTIP Governance Committee resolution. | Reports to Competitiveness Business Unit; all Stage 5 decisions documented and retained for 3 years |
| Competitiveness Business Unit (CBU) | First-instance decision-maker for matters escalated by OECS TSIE (e.g., systemic policy violations, government actor complaints, large-scale IP disputes) | Can confirm content removal, reinstate content, issue final warnings, suspend accounts for up to 30 days, permanently restrict features, permanently deactivate accounts (subject to KTIP Governance Committee notification), and close all complaint categories except those requiring KTIP Governance Committee resolution. | Reports to RPIU; all Stage 5 decisions documented and retained for 3 years |
| KTIP Governance Committee | Final appeal body for all contested Stage 5 decisions; | Final and binding authority on all appealed matters. Can overturn, modify, or uphold any Stage 5 decision. Can direct the OECS TSIE to take any action within platform governance powers. Cannot instruct actions requiring OECS legal proceedings. | Reports to RPIU; decisions published in anonymised escalation summary reports |
| OECS Commission Legal Unit (OL) | Mandatory consultant for IP complaints above a defined threshold, all data breach notifications with regulatory implications, government actor complaints, and any matter where legal proceedings are possible or threatened | Advisory only within this framework, no complaint resolution authority. Legal opinions provided within 48 hours (priority) or 5 business days (standard). | Reports to OECS Commission Director-General |
| Regional Project Implementation Unit (RPIU) | Receives quarterly anonymised complaint summary from OECS TSIE; may direct a governance review of framework policy if complaint patterns indicate systemic issues; does not adjudicate individual complaints | No individual complaint authority. Can direct policy-level reviews. Receives escalation summary reports from Innovation Governance Committee | Reports to OECS Commission and World Bank |
| Complainant / Reporting Party | Submits complaint with supporting evidence; responds to information requests within defined timelines; participates in resolution process in good faith | No decision authority. Has the right to: receive timely updates, provide evidence, respond to preliminary findings, and appeal Stage 5 decisions within 10 business days. | Subject to KTIP Acceptable Use Policy; bad faith or vexatious complaints are themselves Acceptable Use Policy violations |
| Respondent / Subject of Complaint | Receives notification of complaint; has the right to submit a response; participates in Stage 4 review process | No decision authority in the complaint process. Has the right to: be notified of any complaint and its category, submit a written response, review evidence relied upon (subject to complainant privacy), and appeal any adverse Stage 5 decision. | Subject to KTIP Acceptable Use Policy; failure to respond to a reasonable information request within the defined timeline does not prevent a decision being made on the evidence available |

### Issue Classification Matrix

All complaints and reports are classified at triage (Stage 2) using the matrix below. Classification determines the applicable response time, the decision-making authority, and whether temporary protective action is required before a full review. Misclassification must be corrected as soon as identified; the clock resets to the correct category at the point of reclassification.

##### Table 9: Issue Classification Matrix

| Category | Severity | First Response | Decision | Decision Authority | Examples |
| --- | --- | --- | --- | --- | --- |
| Safety - Imminent Harm | P0 - Critical | 1 hour | 4 hours | System Administrator (immediate) + OECS TSIE (confirm within 4 hrs) | Threat of violence, self-harm content, doxing, child safety concern, credible threat of physical harm to a named individual |
| Safety - Serious but Not Imminent | P1 - High | 2 hours | 8 hours | OECS TSIE | Harassment campaign, coordinated targeting of a user, intimidation, severe hate speech, sexual harassment |
| Data Breach / Unauthorised Data Access | P0 - Critical | 1 hour | 4 hours (containment); legal notification per data protection law timeline | OECS TSIE + OECS Legal Unit | Unauthorised access to user data, accidental public exposure of private data, data exfiltration from platform systems |
| IP Complaint - Large Scale (>10 works or commercial use) | P1 - High | 4 hours | 5 business days | OECS TSIE + OECS Legal Unit | Copyright holder claims multiple works are reproduced without licence; claim involves commercial value above EC$10,000 |
| IP Complaint - Single Work | P2 - Medium | 1 business day | 3 business days | OECS TSIE | Single unauthorised reproduction of a research paper, photograph, or other creative work |
| AUP Violation - Serious (hate speech, impersonation, fraud) | P1 - High | 4 hours | 2 business days | OECS TSIE | Impersonation of a named individual or institution; content designed to deceive investors; organised spam campaign |
| AUP Violation - Standard (incivility, spam, minor misuse) | P3 - Low | 1 business day | 5 business days | System Administrator | Single abusive message, off-topic spam posting, mild AUP breach by first-time offender |
| Privacy / Data Correction Request | P2 - Medium | 1 business day | 10 business days | OECS TSIE | Request to correct inaccurate profile data; right to erasure request; data portability request |
| Access Dispute - Account Suspension | P2 - Medium | 1 business day | 3 business days | OECS TSIE | User disputes that their account suspension was applied incorrectly or without basis |
| Access Dispute - Verification Denial | P3 - Low | 1 business day | 5 business days | System Administrator | Mentor or investor disputes that their verification was refused without adequate reason |
| Moderation Dispute - Content Removal | P3 - Low | 1 business day | 5 business days | OECS TSIE (reviews System Administrator decision) | User disputes that their forum post, resource, or project was removed incorrectly |
| Systemic / Policy-Level Complaint | P1 - High | 1 business day | Referred to KTIP Governance Committee within 5 business days | KTIP Governance Committee | Complaint alleges a systematic bias in the moderation system; government actor complaint about platform policy; complaint involving platform management personnel |

Dispute Resolution Clock: The clock starts at the moment a complaint is received and acknowledged in the KTIP complaint register, not at the moment it is assigned to a handler. The clock pauses only when the handler is formally awaiting a mandatory response from the complainant or respondent, and resumes immediately upon receipt of that response or expiry of the response deadline (whichever is earlier).

### Special Procedures

#### Complaints Involving Platform Management Personnel

Where a complaint alleges misconduct, bias, or procedural impropriety by the System Administrator, the complaint must be escalated immediately to the OECS TSIE, bypassing the System Administrator. Where the complaint involves the OECS TSIE, it is escalated directly and immediately to the CBU. Platform management personnel named in a complaint have no role in its investigation.

#### Coordinated or Mass Complaint Campaigns

Where the platform receives multiple complaints about the same content, user, or issue within a short window - indicating a potential coordinated campaign, the System Administrator must flag this to the OECS TSIE within 2 hours. The OECS TSIE determines whether the complaints represent genuine independent concerns or a coordinated targeting effort. Where a coordinated campaign is identified, complaints may be consolidated into a single case and the organiser of the campaign may themselves be subject to an AUP investigation.

#### Vexatious and Bad Faith Complaints

A complaint is vexatious where it is submitted with no reasonable basis, with the intention of harassing the respondent or the platform management personnel, or as a repetition of a previously resolved matter without new evidence. Vexatious complaints are closed at Stage 2 (Triage) with a documented reason. A complainant who submits three or more vexatious complaints within a 12-month period may be subject to an AUP investigation for misuse of the complaints process. The determination that a complaint is vexatious must be made by the OECS TSIE, not the System Administrator, and must be communicated to the complainant with the specific reason.

#### Emergency Takedown (Imminent Safety Risk)

Where the System Administrator identifies content that poses an imminent and credible risk of physical harm to a named individual or group, for example, a direct threat of violence, content facilitating self-harm, or content disclosing the private location of a person at known risk, the System Administrator may execute an immediate content restriction (Stage 3) without waiting for Stage 2 Triage to be completed. The OECS TSIE must be notified within 15 minutes of the emergency action. Stage 2 Triage is completed within 1 hour of the emergency action. The emergency action is documented immediately in the Complaint Register. OECS Commission Legal Unit is notified within 1 hour. National law enforcement is notified via the Legal Unit where the content indicates a criminal threat.

### Cross-Border and Multi-Jurisdiction Matters

Given that KTIP users are located across twelve OECS member states and may include diaspora users in additional jurisdictions, complaints may engage the laws of multiple territories. Where a complaint involves data protection, IP rights, or consumer protection obligations arising in a specific OECS member state, the OECS TSIE must obtain a legal opinion from the OECS Commission Legal Unit on which jurisdiction's law applies and any specific obligations it creates. KTIP does not provide legal advice to users; users with jurisdictional legal questions are directed to competent legal counsel in their territory.

### Confidentiality of the Process

The existence of a complaint, the identity of the complainant, the identity of the respondent, the evidence submitted, and the content of any Stage 4 investigation or Stage 5 decision are confidential to the parties and the platform management personnel. Confidentiality may be broken only where: required by law or a lawful order; required to implement a Stage 5 decision (e.g., notifying a funder that a challenge participant has been disqualified); or where the safety of a third party requires disclosure. Anonymised aggregate complaint data will be shared with the RPIU in the quarterly summary. No individually identifiable information is published.

# Intellectual Property Framework

This framework covers all intellectual property arising from, shared through, or processed on the KTIP platform. It applies to:

- Content IP: Original works uploaded or created by users, such as research papers, datasets, course materials, project documentation, presentations, photographs, code, designs, and multimedia content.

- Innovation IP: Ideas, prototypes, inventions, processes, and business models developed in whole or in part through KTIP tools including challenge workspaces, project collaboration hubs, and mentorship sessions.

- Institutional IP: Materials contributed by universities, research institutions, government agencies, and private sector organisations acting through their staff or student members on KTIP.

- AI-Assisted Content: Content generated with the material contribution of AI tools where a human user has directed, shaped, or substantially modified the output.

- Platform-Generated Data: Analytics, aggregated usage data, and metadata generated by the platform in connection with user activity.

- Third-Party IP: Commercially or openly licensed materials incorporated by users into their KTIP contributions.

## Cross-Border Legal Context

KTIP operates across twelve OECS member states, each with its own national copyright, trademark, and patent legislation. The IP framework establishes platform-level defaults that are designed to be consistent with the intellectual property laws of all OECS jurisdictions. However, users and institutions will be strongly advised that:

- Copyright laws of each OECS member state apply to works created by residents of or registered in that territory. KTIP's IP framework does not override national law.

- Patents must be registered in every jurisdiction where they are intended to be enforced. KTIP's facilitation of a patent-generating collaboration does not confer or secure patent rights in any territory.

- MOUs and formal agreements between institutions may establish ownership and usage terms that supersede the KTIP defaults in this framework. Where such agreements exist, they take precedence.

- Where national laws conflict, the OECS Commission Legal Unit will advise on the applicable law, and the Innovation Governance Committee will determine the platform-level position. Users are directed to seek competent legal counsel in their territory for specific legal advice.

- Harmonisation principle: The KTIP IP policy is designed to harmonise differences in the legal frameworks resulting from contributions received from different OECS countries, reducing negotiation costs while maintaining legal integrity.

## Guiding Principles

The following ten principles were validated through stakeholder workshops as the foundation of the KTIP IP framework. All platform policies, user agreements, and co-creation agreement templates will be drafted in conformity with these principles.

- Clarity of Ownership: Users and institutions must know, at the moment of contributing any content or idea to KTIP, exactly who owns or controls that material and under what terms it can be used by others. KTIP's Terms of Use and profile-level permission settings make ownership visible and unambiguous for every asset on the platform.

- Permission by Design: KTIP only uses, shares, displays, adapts, or retains content where the required permission is explicit and recorded. Permissions are built into the platform workflow and users are prompted to grant or withhold specific permissions at the point of upload, project creation, and collaboration initiation. Owners are notified when another user requests access to their material. Changes to contributed materials require approval or rejection by the owner before they take effect. All permissions are logged for audit purposes.

- User Trust and Fair Notice: Users receive clear, plain-language information about their IP rights and responsibilities before and at the moment of contributing to KTIP. This includes what permissions they are granting to the platform, what rights they retain, what other users can and cannot do with their content, and how to raise an IP complaint. The OECS Commission will produce short video guides on fair use, content sharing, and IP responsibilities for KTIP users, available in English.

- Openness with Protection: Reusable resources and collaborative outputs are actively encouraged on KTIP as engines of regional innovation. Open licensing is supported and promoted. At the same time, confidential information, private data, and creator rights are protected through access controls, confidentiality marking, and a robust complaints and takedown process. Openness and protection are not in conflict; KTIP provides the tools for both to coexist.

- Attribution and Recognition: Creators, institutions, funders, and collaborators receive appropriate recognition wherever their materials are uploaded on KTIP. Content owners' profiles are linked to their contributions. Where content is monetised through exposure gained on the platform, no financial claim accrues to the OECS Commission, the economic benefit belongs to the creator.

- Institutional Autonomy and Regional Consistency: Participating institutions retain their own IP rights and may configure their own content access and permission settings within the KTIP.

- Data Protection and Confidentiality Alignment: IP governance on KTIP is aligned with privacy, confidentiality, cybersecurity, role-based access control, and data-sharing safeguards. Users are proactively reminded not to inadvertently release their rights or the rights of others through the data they share. The KTIP platform adheres to the data protection frameworks applicable in each OECS member state and to internationally recognised best standards where domestic frameworks are silent.

- Accessibility and Inclusion: KTIP permits and supports adaptations of content needed for accessibility, inclusion, translation, and user support, including screen-reader formats, language localisation, and alternative format conversions, subject to applicable legal constraints. Accessibility adaptations do not constitute infringement under this framework where they are non-commercial and support a user's access to educational or collaboration content.

- Platform Efficiency: Standard agreement templates, model contracts, and reusable guidance materials are provided by KTIP to reduce the time and cost of IP negotiation for every collaboration. KTIP does not commit to cost savings for individual parties but provides the infrastructure that makes efficient, lower-cost collaboration possible.

- Responsible Innovation: AI tools, analytics, and emerging technologies used on or through KTIP are governed by principles of transparency, human oversight, data quality, fairness, and accountability. AI-assisted content requires a human review before publication. AI's role in content creation is disclosed.

## Ownership Rules by Scenario

The default ownership position for all IP created, contributed, or processed through KTIP is set out below. These defaults apply where no separate written agreement, such as a Co-Creation Agreement, institutional MOU, challenge-specific IP terms, or industry partnership agreement establishes a different position. Where a separate agreement exists, it governs and where it is silent on a point, these defaults apply.

##### Table 10: Intellectual Property Ownership Rules on the KTIP

| Scenario | Default Ownership | Platform Permission Granted | Attribution / Reuse Rule | Required Documentation |
| --- | --- | --- | --- | --- |
| User uploads original content | Creator or their employing institution retains all ownership rights | Non-exclusive permission for platform to host, display, store, and make accessible to authorised users only | Must be cited by any user who references or builds on it. Owner's permission required for reuse beyond viewing. | Covered by KTIP Terms of Use accepted at registration; owner confirms at upload |
| Institution contributes materials | Institution or named creator retains ownership, subject to institution's own IP policy | Permission for access and reuse within OECS platform network as defined in the institutional MOU | Copies and derivatives restricted to copyright-permitted uses. Attribution to institution and named creator. | Signed institutional MOU or participation agreement; KTIP Terms of Use |
| Student-created works (individual) | Student retains rights unless their institution's IP policy provides otherwise or a separate agreement applies | Permission for learning, assessment, display, moderation, and archival purposes on KTIP | Student work must be cited where used. No commercial reuse by the platform or third parties without student consent. | Included in student user agreement accepted at registration; institutional MOU where applicable |
| Joint or co-created outputs | Ownership agreed between participants before work begins; KTIP default is equal co-ownership if no agreement is made | Collaboration agreement must define use, publication, commercialisation, and attribution terms | All co-creators retain rights; no co-creator may commercialise without consent of other co-creators | Co-Creation Agreement (KTIP standard template); Partnership Agreement where applicable; dispute resolution clause mandatory |
| Work commissioned from a vendor or consultant | Contract must specify ownership, licence, and handover rights. KTIP default: client retains ownership where fully funded. | OECS/commissioning party secures sufficient rights for use, modification, maintenance, and transfer | Mutual consent required for any public attribution of vendor or consultant | Signed service contract with IP clause; included in KTIP vendor procurement standard |
| Platform-generated analytics | Owned by KTIP under OECS Commission governance; not owned by individual users | Limited to authorised, transparent, and accountable platform management purposes. Not commercialised or shared externally without express consent. | Policy from the OECS Commission takes precedence; data is not attributed to identifiable users | KTIP Data Governance clause in Terms of Use; KTIP Data Protection Policy |
| Third-party or openly licensed resources | External owner or licence holder; KTIP holds no ownership claim | Use only within the terms of the applicable licence; attribution and restrictions strictly observed | Attribution as required by licence. Non-commercial and share-alike restrictions must be honoured. | Rights clearance checklist completed at upload; licence type tag applied to resource |
| AI-assisted content | Depends on AI tool's terms of service, the nature of input materials used, and the human contribution. KTIP default: the human contributor who directed and substantially shaped the output is treated as the author. | Requires transparency declaration and quality review before publication; rights check on input materials | Cite AI tool used and describe human contribution. Where AI generated a full first draft, this must be disclosed. | AI Content Disclosure form completed at submission; human review confirmed before publication |
| Challenge / hackathon submissions | Ownership by submitting team or individual, unless the challenge-specific IP Terms provide otherwise (e.g., sponsor buyout option, licence-back) | Challenge organisers receive a limited licence to evaluate, display publicly, and promote winning entries. No broader use without written consent. | Team name and institution cited in any public promotion of results. Winning teams retain ownership. | Challenge-Specific IP Terms accepted at submission; Co-Creation Agreement for team submissions |

## Co-Creation Safeguards by Scenario

Co-creation is at the core of the innovation mission for the KTIP. The scenarios below map the specific safeguards required for each major co-creation context on the platform, drawing directly from stakeholder-identified risks.

##### Table 11: Co-Creation Safeguards on the KTIP

| Co-Creation Scenario | Participants | Ownership / Permission Safeguard | Confidentiality Safeguard | Platform Mechanism |
| --- | --- | --- | --- | --- |
| Entrepreneur collaborations | Entrepreneurs | Ownership disputes over designs, data, or outputs prevented by mandatory industry partnership agreement before project commences. Agreement must address: who owns what, sponsor's rights to background IP, and student IP protections. | Confidential business/project information handled under NDA. Weak security risks addressed by mandatory role-based access and confidentiality classification of all project materials. | Co-creation Agreement template; NDA/confidentiality template; security classification marking; role-based access control |
| Industry-sponsored project | Institution, students, private-sector partner | Ownership disputes over designs, data, or outputs prevented by mandatory industry partnership agreement before project commences. Agreement must address: who owns what, sponsor's rights to background IP, and student IP protections. | Confidential business information handled under NDA. Weak security risks addressed by mandatory role-based access and confidentiality classification of all project materials. | Industry Partnership Agreement template; NDA/confidentiality template; security classification marking; role-based access control |
| Innovation challenge or hackathon | Entrepreneurs, students, institutions, mentors, industry partners | IP Terms accepted at registration. Ownership documentation completed at team formation - the platform requires each team to designate ownership structure (individual, shared, or institutional) before submission. | Strict confidentiality controls over submitted materials. Platform gate-keepers ensure only authorised evaluators access pre-public submissions. | Challenge IP Terms (per challenge); Confidentiality marking tool; Role-based access control; evaluator NDAs |
| Joint research collaboration | Researchers, institutions, ministries, partners | IP disputes are pre-empted by a mandatory Co-Creation Agreement at project initiation covering: ownership of outputs, dataset ownership, publication rights, and commercialisation authority. | Ethical research protocols apply. Structured security for sensitive datasets. Tension between open scientific publication and commercial or privacy restrictions managed by explicit declaration at project setup. | Research Collaboration Agreement template; ethical protocols checklist; dataset access controls; publication approval workflow |

## Intellectual Property Protection Mechanisms

KTIP deploys several protection mechanisms to give effect to the principles and ownership rules in this framework. Each mechanism has a designated responsible actor, a defined process, and an agreed standard.

##### Table 12: Intellectual Property Protection Mechanisms on the KTIP

| Protection Mechanism | Purpose | Responsible Actor | Process and Standard |
| --- | --- | --- | --- |
| Attribution Standard | Rules for naming creators, institutions, funders, and collaborators wherever their materials or outputs are used or reused on KTIP. | OECS Commission (sets policy); all users (apply standard) | OECS to develop and publish an attribution standard as part of the Terms of Use. Users self-identify as creator at point of upload. Where content is shared or cited, the platform automatically displays the contributor's profile link and attribution tag. Non-compliance with attribution obligations is an AUP violation. |
| Rights Clearance Checklist | Ensures users confirm that they have the rights to upload the content they are submitting, that third-party permissions are in place, and that the applicable licence type has been identified. | SDT (Design), Users (complete) | Automated checklist launched at every content upload requiring: (a) confirmation of ownership or authorisation; (b) identification of any third-party IP included; (c) selection of the applicable licence type; (d) acknowledgement that the Terms of Use govern use of the content on the platform. User Agreement auto-launches before first platform access. |
| Confidentiality Marking Tool | Labels content as Confidential, Restricted, Internal, Public, or Draft, controlling who can view, download, edit, or share each asset. | SDT (builds and maintains); Users (apply labels) | Marking is applied by the content owner at upload or project creation and may be updated by the owner at any time. The system enforces access restrictions based on the applied marking in accordance with the approved rules and standards. Role-based access control enforces the marking. |
| Role-Based Access Control (RBAC) | Defines who can view, upload, edit, export, delete, approve, or publish materials based on their verified role on the platform. | SDT (configures); OECS TSIE (approves rules) | Access rights are configured by the technical team in accordance with the approved access matrix defined in the KTIP administrators. |
| Takedown and Complaints Workflow | Provides a structured, time-bound process for reporting, triaging, temporarily restricting, investigating, deciding upon, and appealing IP infringement complaints and other content removal requests. | Systems Administrator (raises alert and executes technical actions); OECS TSIE (decides); OECS Legal Unit (advises on complex matters) | Governed in full by the KTIP Escalation, Complaints, Takedown and User Redress process outlined in this document. |
| Retention and Exit Rules | Defines what happens to materials on KTIP after a project ends, a user account is closed, an institution withdraws from the platform, or the platform migrates to a new technical infrastructure. | OECS Commission (set policy); Technical Specialist EMIS and Virtual Campus or a designated SDT Representative (executes) | At project close: materials are archived for a defined period (minimum 3 years) in a secure, access-restricted state. At account closure: materials owned by the user are either archived to support account reactivation, or deleted at the user's request, per the KTIP Data Protection Policy. At platform migration: data portability in a standard, open format is mandatory. Retention periods and exit processes are communicated to users at registration and at project close. |

## Terms of Use - IP-Related Obligations

The KTIP Terms of Use Agreement is a separate document but the following table sets out the minimum IP-related provisions that must be included in the Terms of Use to give effect to this framework. All items below will be drafted and legally reviewed before the platform accepts its first registered user.

##### Table 13: Intellectual Property Considerations for Terms of Use Agreement

| Terms Topic | Minimum Content Required | User Category | Pre-Launch Requirement |
| --- | --- | --- | --- |
| Acceptance and applicability | Who must accept the Terms of Use (all registered users and authorised visitors); when acceptance occurs (before first platform access, signified by an active affirmative action — not implied by browsing); how acceptance is recorded and auditable. | All users | Critical — must be in place before any user registration opens |
| IP ownership clause | Clear statement that users retain ownership of their original content; what non-exclusive rights are granted to KTIP; that KTIP does not claim, acquire, or commercialise user IP; that institutional IP is subject to the relevant institutional policy; that OECS Commission owns platform-generated analytics. | All users | Critical - must be in place before any content upload functionality is enabled |
| Content upload responsibilities | Confirmation that users have the rights to upload the content they are submitting; that third-party permissions are obtained; that the applicable licence type has been identified; that confidential content is appropriately marked; that AI-generated content is disclosed. | All users with upload rights | Critical - must be in place before Knowledge Library and project workspaces go live |
| Non-commercialisation clause | Explicit prohibition on users commercialising other users' content without the content owner's written consent; explicit prohibition on KTIP commercialising user content; statement that economic benefits from commercialisation accrue to the creator. | All users | Critical - must be in place before any commercial challenge or investment-related feature goes live |
| Permitted and prohibited uses | Positive list of permitted uses (learning, teaching, collaboration, administration, innovation, authorised research); negative list of prohibited uses (infringement, harassment, misinformation, unauthorised data extraction, security misuse, impersonation). | All users | Critical - must be in place before beta launch |
| Attribution obligations | Requirement to cite the original creator and institution when referencing or building on another user's content; prohibition on presenting others' work as one's own; how attribution must be displayed on the platform. | All users | High priority - must be in place before any collaborative project tools go live |
| Licence to the platform | Statement of the specific non-exclusive licence granted by the user to KTIP: to host, store, display, reproduce for technical operation, adapt for accessibility, and share within the authorised OECS network. No broader rights granted. | All users | Critical - must be in place before any content upload functionality is enabled |
| Open licence guidance | Information on how to apply a Creative Commons or other open licence to resources in the Knowledge Library; what each licence type permits; how open licences interact with the KTIP Terms of Use. | Users contributing to Knowledge Library | High priority - must be in place before Knowledge Library opens to public contributions |
| AI content disclosure | Obligation to disclose where AI tools were materially used in creating content uploaded to KTIP; obligation to complete a human review before publication; how AI-assisted content is attributed. | All users with upload rights | High priority - must be in place before AI tool integrations are enabled on the platform |
| Account security and user responsibilities | Password management obligations; prohibition on account sharing; obligation to report suspected unauthorised access; accurate and current profile information requirements. | All users | Critical - must be in place before any user registration opens |
| Complaints pathway reference | Reference to the KTIP Escalation, Complaints, Takedown and User Redress process; how to report an IP complaint; what temporary protective actions may be taken pending investigation; right of appeal. | All users | Critical - must be in place before beta launch |
| Retention and exit | What happens to the user's content if their account is closed; data portability rights; retention period for archived content; right to request deletion subject to KTIP's legal retention obligations. | All users | High priority - must be in place before any account can be deactivated |

# Technical Readiness & Deployment Plan

## Technology Stack and Architecture

The KTIP will be built on modern, cloud-native, proprietary architecture with additional on-premise redundancies that avoids vendor lock-in, supports regional data sovereignty, and can be maintained and extended by regional technical talent (OECS Software Development Team):

### Frontend

- Framework: React 18.3+ with TypeScript

- Build Tool: Vite 5.4+

- Styling: Tailwind CSS 3.4+

- Icons: Lucide React

- State Management: React Context API

### Backend

- Platform: Supabase (PostgreSQL + Edge Functions)

- Database: PostgreSQL 15+

- Authentication: Supabase Auth (Email/Password)

- Storage: Supabase Storage (Images, Documents)

- Edge Functions: Deno runtime on Supabase Edge Network

### Infrastructure

- Hosting: Supabase Cloud (Global CDN)

- Database: Managed PostgreSQL with automated backups

- Storage: Object storage with CDN delivery

- Security: Row Level Security (RLS) policies, SSL/TLS encryption

- AI Services: Open-source NLP models (e.g., spaCy, HuggingFace) hosted within the KTIP environment for matchmaking and content tagging. Avoids dependency on proprietary AI APIs.

- Integrations: Zapier/webhook-based integrations with Zoom/Google Meet for events and calls, Mailchimp/Sendgrid (notifications), slack for team communication, GitHub for project repos, LinkedIn for professional networking, Calendar sync (Google/Outlook)

## Environments

##### Table 14: Environment Breakdown

| Environment | Purpose | Configuration |
| --- | --- | --- |
| Development | Active feature development by technical team and approved contractors | Isolated sandbox with synthetic data; no real user data; CI/CD pipeline integration |
| Staging / UAT | Pre-release testing; user acceptance testing with select beta users; integration testing | Mirror of production infrastructure; refreshed with anonymised production data |
| Production | Live platform accessed by all registered users | High-availability configuration; auto-scaling; 99.5% uptime SLA; daily backups; disaster recovery tested quarterly |

## Deployment and Release Process

- Code review and approval

- TypeScript compilation check

- Build production bundle (npm run build)

- Run database migrations

- Deploy to Supabase hosting

- Deploy edge functions

- Verify deployment

- Monitor for errors

## Security, Compliance, and Monitoring

- Vulnerability Management: Monthly automated vulnerability scans (OWASP ZAP, Snyk); quarterly manual penetration tests by third-party; critical vulnerabilities patched within 48 hours.

- Data Residency: User data to be stored in jurisdictions compliant with applicable OECS member state data protection requirements.

- Monitoring: 24/7 application performance monitoring (Datadog or open-source equivalent); user-facing status page; incident response plan.

- Disaster Recovery: RTO (Recovery Time Objective) of 4 hours; RPO (Recovery Point Objective) of 24 hours. Annual DR drills to be conducted and results reported to Advisory Board.

# Priority Roadmap (Now / Next / After)

## Now: Months 0–3 (Foundation & Launch Readiness)

##### Table 15: Foundation & Launch Readiness Activities

| Activity / Feature | Description | Success Criteria |
| --- | --- | --- |
| Software developers onboarded | Onboarding of OECS Software Development Team | Signed contracts; development environment live |
| Identity & Profile Module (MVP) | User registration, verified profiles, role-based access, email verification | 100 beta users registered from ≥4 OECS states |
| Discovery module (MVP) | Basic keyword and tag-based search across profiles and projects | Search returns accurate results in <2 seconds |
| Matchmaking engine (AI-enhanced) | Personalised recommendations for collaborators, mentors, and opportunities | Recommendation click-through rate ≥25% |
| Projects & Collaboration Hub | Shared workspaces with task management, file sharing, milestones | 10+ active projects; 20+ collaborators engaged |
| Funding & Grants Directory | 20+ funding opportunities listed; eligibility filter; application tracking | Directory accessed by ≥60% of active users monthly |
| Events calendar launched | Display and register for upcoming OECS innovation events | 10+ events listed; 500+ event registrations |
| Analytics Dashboard (internal) | PMU and Advisory Board access to platform activity data | Monthly dashboard reports shared with OECS Commission |
| Knowledge library seeded | 50+ curated resources uploaded; categories established | Resources accessed by 70%+ of beta users |

| Strategic partnerships (Post-Secondary Institutions, BSOs, ESOs, Investors) | Formal integration with Post-Secondary Institutions, Business Support Organizations, Entrepreneurship Support Organizations, Funding Agencies | 50+ users onboarded through partnerships 10+ grant opportunities seeded |
| --- | --- | --- |

## Next: Months 3–6

##### Table 16: Activation & Ecosystem Building Activities

| Activity / Feature | Description | Success Criteria |
| --- | --- | --- |

| System Administrator selected | Onboarding of system administrator | Signed contract |
| --- | --- | --- |

| Virtual Campus Integration | Integration with OECS Virtual Campus; course directory | 50+ course enrolments tracked through KTIP |
| --- | --- | --- |

| Innovation Champions Network | Onboarding of innovation champions in each member state | MOUs signed |
| --- | --- | --- |
| Structured Mentorship Programme | 6-session programme format; scheduling; goal-setting; feedback tools | 20+ active mentorship relationships |
| First Regional Innovation Challenge | Partner with private sector sponsor to launch inaugural KTIP challenge | 35+ challenge submissions from ≥7 OECS states |
| Strategic partner engagement (Post-Secondary Institutions, BSOs, ESOs, Investors) | Continued engagement of Post-Secondary Institutions, Business Support Organizations, Entrepreneurship Support Organizations, Funding Agencies | 100+ users onboarded through partnerships |

## After: Months 6–12

##### Table 17: Scale

| Activity / Feature | Description | Success Criteria |
| --- | --- | --- |
| Regional Technical Support Team Members Selected | Onboarding of RTST members in each member state | Signed contracts |
| Public Impact Dashboard | Public-facing real-time ecosystem metrics and impact data | Dashboard embedded in OECS Commission communications |
| Investor Engagement | Private, verified investor-startup matching environment | 25+ verified investors; 20+ investment-ready startups listed |
| Diaspora Engagement | Dedicated onboarding for diaspora mentors and investors | 50+ diaspora members registered |
| Year 1 impact evaluation | Independent evaluation of platform outcomes against baseline KPIs | Evaluation report published; lessons incorporated in Year 2 plan |

# Quick Wins

The following quick wins are designed to create visible ecosystem activity, generate early media coverage, and validate core platform hypotheses before significant further investment. A critical insight from comparable platform launches (including InnoCentive, Wazoku, and regional initiatives like TECHIE) is that platforms must demonstrate value loudly and early otherwise initial user enthusiasm dissipates before network effects can develop.

##### Table 18: Quick Wins for the Platform

| Quick Win | Description | Owner | Expected Benefit |
| --- | --- | --- | --- |
| KTIP Beta Launch Event | Virtual and in-person launch event. Target 100 registrations. | OECS TSIE + CBU + Communications | Regional visibility; 100+ registrations; media coverage; stakeholder buy-in signal |
| Innovation Champions Network | Recruit 24 Innovation Champions (2 per OECS member state) as community ambassadors. Champions promote KTIP and onboard peers. | OECS TSIE + CBU | Grassroots reach into all 12 member states; 20+ users per champion over 6 months |
| First OECS Hackathon via KTIP | 48-hour virtual hackathon hosted on platform with a regionally relevant challenge theme (e.g., climate resilience, food security). Co-sponsored by private sector. | OECS TSIE + CBU + Communications | 20+ teams of 4 participants; platform stress test; media stories; challenge sponsor relationship |
| Mentor Spotlight Campaign | Weekly social media and platform profiles of KTIP mentors with storytelling content. Cross-posted on OECS Commission channels. | OECS TSIE + Communications | Mentor recruitment; brand trust; community engagement; press coverage |
| First Funding Match | Identify and publicly celebrate first KTIP-facilitated funding connection e.g., entrepreneur connects with a grant opportunity or investor via platform. | CBU + OECS TSIE + Communications | Proof of value narrative; donor confidence; replication signal for users |
| Formalize Partnerships with Post-Secondary Institutions | Sign a formal MOU with Post-Secondary Institutions for student engagement and opportunities | CBU + RPIU + Communications | 100+ student onboarding pipeline; institutional credibility; academic content channel |
| Formalize Partnerships with Strategic Partners in the Innovation Ecosystem | Sign formal MOUs with Strategic Partners like CARICOM CDF, CEDA, ECCB etc. for entrepreneurs and startups etc. | CBU + TSIE | 5 - 10 Organizations onboarding pipeline; |
| Knowledge Library 'Top 10 Resources' | Curate and promote the 'Top 10 Most Useful Resources for OECS Innovators' downloadable guides, funding directories, and toolkits. | OECS TSIE | Immediate library value; content shareability; search engine visibility for KTIP |

# Partnerships & Engagement Plan

The success of the platform is heavily dependent on collaborative partnerships with innovation ecosystem actors (entrepreneurs, post-secondary institutions, funding agencies etc.) in the OECS and beyond. The KTIP is built on the principle of shared value, whereby each actor contributes value in exchange for reciprocal value from the other platform participants. Therefore, to demonstrate this value requires early onboarding of strategic partners and the development of an Innovation Champions Network, comprised of individuals participating in innovative activities across the OECS and whose personal brand can be leveraged to promote additional participation on the platform. These partnerships with established brands and credible agencies will also reinforce the legitimacy of the platform, minimizes skepticism and engenders trust among potential users. Details on the nature of these partnerships, including the roles of each partner type are presented in the following section.

## Priority Strategic Partners

##### Table 19: Partnership Engagement Plan

| Partner Type | Non Exhaustive List of Potential Partners | Level of Engagement | Incentive / Value Exchange | Timeline |
| --- | --- | --- | --- | --- |
| Multilateral/Bilateral Donors | World Bank, IDB, GIZ CDB, EU CDF, CBDF, Compete Caribbean, IDB Lab, IDB Invest | Grant funding, technical assistance, challenge co-sponsorship | KTIP provides ecosystem data, beneficiary reporting, and policy intelligence to donors | Months 1–3 (confirm existing; prospect new) |
| Regional Post-Secondary Institutions/Research Institutions | Dominica State College, Antigua State College, H Livity Stoute College, Clarence Fitzroy Bryant College, Saint Vincent and the Grenadines Community College, Anguilla Community College, T.A. Marryshow CC (Grenada), Sir Arthur Lewis CC (St. Lucia) | Student onboarding, research collaboration | Student, Faculty and Industry connection facilitation | Months 2–6 |
| Private Sector Champions | OECS private sector associations, regional banks and other funding agencies (equity, venture capital, angel) | Challenge sponsorship, membership subscriptions, event co-hosting | Brand visibility, talent pipeline, CSR impact data, deal flow access | Months 1–4 |
| Government Agencies | OECS Commission, National Investment Promotion Agencies, Innovation Departments, Ministries of Education, Trade, Commerce, Economic Development | Data sharing agreements, joint programming, co-promotion | Policy intelligence | Months 2–6 |
| Diaspora Networks | Caribbean Diaspora for Science, Technology & Innovation (CDSTI), national diaspora associations in UK, US, Canada | Ambassador programme, virtual mentorship pipeline, investment facilitation | Reconnection with Caribbean market, professional visibility, social impact | Months 3–9 |
| Technology Partners | Microsoft for Startups, Google for Startups, AWS EdStart, GitHub Education | Cloud credits, software licensing, training resources | Platform stability, reduced infrastructure cost, access to startup ecosystems | Months 1–6 |
| Innovation Intermediaries | Caribbean Export Development Agency, Compete Caribbean, CARICOM Secretariat etc. | Data exchange, cross-referral, co-programming | Extended reach, aligned mandate, complementary data sets | Months 3–9 |

## Planned Events, Challenges, and Campaigns

### Launch and Platform Expansion Activities

EDM-27-WB-1206c KTIP Official Launch - Hybrid 10 August 2026 ¦ Budget: US$40,000

The official regional launch of the KTIP platform, hybrid format combining an in-person anchor event with virtual participation across all OECS Member States. The launch formally introduces the platform to innovators, students, entrepreneurs, industry partners, and government stakeholders, and onboards the first cohort of active users.

- Formally introduce KTIP and demonstrate its key features and functionalities to regional stakeholders.

- Engage and onboard key stakeholders across all OECS Member States.

- Promote cross-border collaboration and knowledge sharing as the platform's core value proposition.

- Raise awareness of the grant discovery, project collaboration, proposal builder, and challenge infrastructure available through the platform.

- Mobilise partnerships and support for the innovation challenge programme.

- Highlight KTIP's role in advancing regional development priorities aligned to sustainable agriculture, blue economy, and sustainable tourism.

##### Table 20: Launch and Platform Expansion Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Pre-Launch Planning and Coordination | 12 May 2026 | 6 Jun 2026 | Venue, agenda, logistics confirmed |
| Stakeholder Engagement and Invitations | 2 Jun 2026 | 25 Jul 2026 | All 9 Member States; industry; PSI leads |
| Programme Development | 20 May 2026 | 5 Aug 2026 | Speakers, demonstrations, panels |
| Platform Readiness and Demonstration | 20 May 2026 | 5 Aug 2026 | Live platform demo environment |
| Communications and Visibility | 15 Jun 2026 | 10 Aug 2026 | Regional media; social; OECS channels |
| Logistics and Event Management | 20 Jun 2026 | 8 Aug 2026 | Venue, AV, catering, virtual stream |
| Event Execution | 10 Aug 2026 | 10 Aug 2026 | Hybrid launch event |
| Monitoring, Documentation, and Reporting | 10 Aug 2026 | 20 Aug 2026 | Attendance; engagement metrics |
| Post-Launch Engagement and Follow-Up | 11 Aug 2026 | 10 Sep 2026 | Follow-up with new registrants |

EDM-27-WB-1206d KTIP Roadshow Expansion Feb 2027 - Jun 2029 ¦ Budget: US$75,000

The KTIP Roadshow delivers interactive in-person and hybrid engagement events across all OECS Member States, activating the platform in each territory and building the critical mass of local innovators, students, and entrepreneurs required for a thriving regional ecosystem. The Roadshow covers two islands per month across February - May 2027, with follow-on periods in subsequent years. Five periods at US$15,000 per period.

- Drive regional awareness, adoption, and active use of KTIP by engaging stakeholders across all OECS Member States.

- Onboard innovators, entrepreneurs, and students in each territory through live platform demonstrations and registration support.

- Build strategic partnerships with national innovation bodies, Ministries of Education, and industry associations in each Member State.

- Stimulate challenge participation by contextualising each OECS territory's specific contribution to regional challenge themes.

##### Table 21: KTIP Roadshow Expansion

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Pre-Roadshow Planning and Coordination | 4 Jan 2027 | 31 Jan 2027 | Logistics, venues, partnerships per island |
| Programme Development | 15 Jan 2027 | 28 Feb 2027 | Territory-specific programme adaptations |
| Platform Readiness | 15 Jan 2027 | 15 Mar 2027 | Platform confirmed stable for regional load |
| Communications and Visibility | 1 Feb 2027 | 30 May 2027 | Territory-specific outreach campaigns |
| Logistics and Event Management | 20 Jan 2027 | 30 May 2027 |  |
| Roadshow Execution - Islands 1 & 2 | 1 Feb 2027 | 28 Feb 2027 |  |
| Roadshow Execution - Islands 3 & 4 | 1 Mar 2027 | 31 Mar 2027 |  |
| Roadshow Execution - Islands 5 & 6 | 1 Apr 2027 | 30 Apr 2027 |  |
| Roadshow Execution - Islands 7 & 8 | 1 May 2027 | 31 May 2027 |  |
| Monitoring, Documentation, and Reporting | 1 Feb 2027 | 30 May 2027 | Per-island adoption metrics |
| Post-Roadshow Follow-Up | 1 Jun 2027 | 30 Jun 2027 | Follow-up with new registrants per territory |

### Knowledge Exchange Activities

Knowledge exchange activities convene regional stakeholders for structured learning, co-creation, and collaborative problem-solving.

EDM-27-WB-1202a Caribbean Innovation Days 2026 1 - 4 December 2026 ¦ Budget: US$150,000

Caribbean Innovation Days 2026 is the flagship knowledge exchange event of the KTIP programme and the first major regional activation following the Official Launch. It is delivered in partnership with Technopole I-NOVA Guadeloupe and French Tech Guadeloupe, giving the OECS innovation ecosystem direct connectivity to the Francophone Caribbean innovation network.

- Leverage Caribbean Innovation Days 2026 as the strategic platform to formally introduce KTIP to the regional innovation ecosystem.

- Strengthen regional innovation capacity across all OECS Member States through curated knowledge exchange sessions, masterclasses, and peer learning.

- Foster collaboration among entrepreneurs, MSMEs, academics, and policymakers across Caribbean territories.

- Accelerate the adoption of innovation-driven solutions to regional development challenges.

- Promote the practical application and scaling of innovative solutions throughout the OECS region.

##### Table 22: Caribbean Innovation Days Planning Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Secure Partnership - Technopole I-NOVA & French Tech Guadeloupe | 1 Apr 2026 | 30 Apr 2026 | MOU and co-branding agreed |
| Pre-Event Planning (venue, agenda, speakers, presenters, facilitators) | 2 Apr 2026 | 30 Nov 2026 | Multi-territory logistics |
| Obtain travel approvals for participants | 1 Oct 2026 | 14 Nov 2026 | OECS Commission approvals process |
| Coordinate Travel and Accommodations | 1 Oct 2026 | 14 Nov 2026 |  |
| Content & Materials Preparation | 1 Sep 2026 | 30 Nov 2026 | Presentations, exhibits, KTIP demos |
| On-Site Execution | 30 Nov 2026 | 5 Dec 2026 | 4-day event |
| Post-Event Follow-Up | 7 Dec 2026 | 30 Dec 2026 | Participant follow-up; KTIP registrations |

EDM-27-WB-1202b KTIP Co-Creation Workshop - Blue Economy 15 - 19 July 2027 ¦ Budget: US$62,500

A structured co-creation workshop bringing together innovators, researchers, entrepreneurs, coastal community representatives, industry partners, and government officials to develop practical innovation solutions for blue economy challenges across the OECS. The Blue Economy theme is selected as a priority given the OECS Member States' direct dependence on marine resources and the region's vulnerability to climate change impacts on ocean health and fisheries.

- Induce active participation on the KTIP through immersive capacity building, networking, and joint problem-solving.

- Generate co-created innovation proposals addressing specific blue economy challenges (fisheries management, marine conservation, coastal tourism, ocean energy).

- Build cross-territory partnerships between innovators and industry players with shared blue economy interests.

- Document and publish workshop outputs as KTIP knowledge resources available to the full regional innovation community.

##### Table 23: Blue Economy Co-Creation Workshop Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Strategic Design & Concept Development | 1 Aug 2027 | 17 Sep 2027 | Challenge framing; facilitator design |
| Platform Configuration & Integration (KTIP) | 1 Sep 2027 | 12 Nov 2027 | Workshop tools; collaboration spaces |
| Governance & Coordination | 13 Sep 2027 | 19 Nov 2027 | Multi-territory participant coordination |
| Stakeholder Engagement & Outreach | 13 Sep 2027 | 19 Nov 2027 | Blue economy industry & govt. partners |
| Content & Materials Preparation | 1 Oct 2027 | 12 Nov 2027 | Challenge briefs; resource packs |
| Workshop Execution | 15 Nov 2027 | 19 Nov 2027 | 5-day co-creation workshop |
| Documentation & Knowledge Capture | 15 Nov 2027 | 26 Nov 2027 | Outputs published on KTIP |
| Post-Workshop Engagement & Continuity | 20 Nov 2027 | 15 Dec 2027 | Follow-up with participant teams |
| Monitoring & Evaluation | 15 Dec 2027 | 15 Dec 2027 | M&E report to RPIU |

EDM-27-WB-1202c KTIP Co-Creation Workshop - Sustainable Agriculture February 2028 ¦ Budget: US$62,500

A structured co-creation workshop focused on innovation solutions for sustainable agriculture challenges across the OECS. The Sustainable Agriculture theme addresses the region's food security vulnerabilities, climate-adaptive farming needs, and opportunities for agri-innovation in small island contexts. This workshop follows the Blue Economy Workshop and applies the same facilitation methodology.

- Generate co-created innovation proposals for sustainable agriculture challenges (climate-adaptive crops, soil health, water management, agri-tech, food processing).

- Build cross-territory connections between agricultural innovators, rural entrepreneurs, and regional food system stakeholders.

- Develop actionable project concepts eligible for submission to the Sustainable Agriculture Challenge and for grant application through the KTIP grants module.

##### Table 24: Sustainable Agriculture Co-Creation Workshop Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Strategic Design & Concept Development | 1 Feb 2028 | 17 March 2028 | Challenge framing; facilitator design |
| Platform Configuration & Integration (KTIP) | 1 Mar 2028 | 12 May 2028 | Workshop tools; collaboration spaces |
| Governance & Coordination | 13 Mar 2028 | 19 May 2028 | Multi-territory participant coordination |
| Stakeholder Engagement & Outreach | 13 Mar 2028 | 19 May 2028 | Blue economy industry & govt. partners |
| Content & Materials Preparation | 1 April 2028 | 12 May 2028 | Challenge briefs; resource packs |
| Workshop Execution | 15 May 2028 | 19 May 2028 | 5-day co-creation workshop |
| Documentation & Knowledge Capture | 15 May 2028 | 26 May 2028 | Outputs published on KTIP |
| Post-Workshop Engagement & Continuity | 20 June 2028 | 15 June 2028 | Follow-up with participant teams |
| Monitoring & Evaluation | 15 June 2028 | 15 June 2028 | M&E report to RPIU |

### Innovation Inducement Activities

Inducement instruments are the activation core of the KTIP's mission to drive innovation activity. They use prizes, competitions, open challenges, and hackathons to motivate concrete participation from innovators, students, and entrepreneurs across the OECS.

EDM-27-WB-1203a KTIP Platform Onboarding & Prize Award - OECS Super Regional Robotics Competition 16 - 21 March 2027 ¦ Budget: US$25,000

Building on the user validation activity conducted at the March 2026 Robotics Competition, this activity deploys the production KTIP platform which will have completed its Architecture Lock-In and Official Launch by this date at the 2027 OECS Super Regional Robotics Competition. It delivers an innovation prize award and onboards competition participants as active KTIP members. Delivered in partnership with the Eastern Caribbean Robotics and Innovation Association (ECRIA).

- Onboard competition participants, schools, and innovation stakeholders as active KTIP platform members.

- Award an innovation prize for the most outstanding innovation solution submitted through the KTIP platform at the competition.

- Foster collaboration between student innovators and KTIP's broader community of mentors, investors, and entrepreneurs.

- Build strategic partnerships with ECRIA and participating schools to sustain KTIP engagement beyond the competition.

##### Table 25: OECS Super Regional Robotics Competition Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Secure Partnership with ECRIA | 15 Jun 2026 | 15 Aug 2026 | Partnership agreement formalised |
| Strategic Planning & Concept Design | 1 Aug 2026 | 15 Sep 2026 | Prize structure; onboarding pathway |
| Pre-Event Planning | 15 Sep 2026 | 3 Nov 2026 | Logistics; platform configuration |
| Travel approvals for participants | 15 Nov 2026 | 1 Jan 2027 |  |
| Coordinate Travel and Accommodations | 1 Jan 2027 | 28 Feb 2027 |  |
| Platform Integration (KTIP Enablement) | 1 Dec 2026 | 15 Feb 2027 | Challenge submission module live |
| Content & Materials Preparation | 1 Jan 2027 | 15 Mar 2027 | Prize brief; judging criteria |
| On-Site Execution | 16 Mar 2027 | 21 Mar 2027 | Competition; prize award ceremony |
| Post-Event Follow-Up | 22 Mar 2027 | 15 Apr 2027 | Onboarding follow-up; KTIP activation |

EDM-27-WB-1203b KTIP Challenges & Call for Solutions - Sustainable Agriculture 17 - 19 May 2027 ¦ Budget: US$75,000

An open regional innovation challenge calling on innovators, students, and entrepreneurs to submit solutions to defined sustainable agriculture challenges affecting OECS Member States. Solutions are submitted through the KTIP platform's Proposals module, judged by a panel of regional and international experts, and awarded prizes. The challenge is designed to generate actionable innovation outputs with pathways to implementation and scaling.

- Encourage innovators, entrepreneurs, researchers, and practitioners to engage with KTIP by developing and submitting solutions to key regional agricultural challenges.

- Generate a shortlist of implementable innovation solutions that address food security, climate-adaptive farming, and agricultural value chain development in OECS Member States.

- Identify and support promising innovators for further development through KTIP's mentorship and grant discovery functions.

##### Table 26: Challenges & Call for Solutions - Sustainable Agriculture Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Strategic Planning & Concept Design | 15 Jan 2027 | 28 Feb 2027 | Challenge brief; prize structure defined |
| Governance & Coordination | 1 Feb 2027 | 18 May 2027 | Judging panel constituted |
| Platform Integration (KTIP Enablement) | 10 Feb 2027 | 10 May 2027 | Submission workflow live on KTIP |
| Partnerships & Resource Mobilisation | 1 Feb 2027 | 30 Apr 2027 | Industry judges; prize sponsors |
| Communications & Outreach | 1 Mar 2027 | 14 May 2027 | Open call circulated regionally |
| Participant Onboarding & Capacity Building | 1 Apr 2027 | 14 May 2027 | Pre-submission workshops |
| Challenge Execution | 17 May 2027 | 19 May 2027 | Submissions close; final pitches |
| Judging & Awards | 21 May 2027 | 21 May 2027 | Prize ceremony |
| Post-Challenge Support | 22 May 2027 | 30 Jun 2027 | Winner development support |
| Monitoring, Evaluation & Reporting | 15 Jun 2027 | 30 Jun 2027 | M&E report to RPIU |

EDM-27-WB-1203f Eco-Ventures Regional Innovation Challenge Partnership July 2027 ¦ Budget: US$5,000

A partnership contribution to the Eco-Ventures Regional Innovation Challenge, enabling KTIP to co-brand and co-promote a challenge focused on sustainable tourism solutions. KTIP participants are invited to submit entries through the KTIP platform, and the joint challenge amplifies KTIP's reach to the sustainable tourism innovation community.

##### Table 27: Eco-Ventures Regional Innovation Challenge Partnership Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Platform Integration (KTIP Enablement) | 1 Apr 2027 | 18 Jul 2027 | KTIP submission pathway for Eco-Ventures |
| Joint Communications | 10 Apr 2027 | 10 Jul 2027 | Co-branded outreach |
| Participant Onboarding & Capacity Building | 15 Jun 2027 | 14 Jul 2027 | KTIP onboarding for Eco-Ventures participants |
| Challenge Execution | 1 Jun 2027 | 14 Jul 2027 |  |
| Judging & Awards | 19 Jul 2027 | 20 Jul 2027 | Prize award |
| Post-Challenge Support | 21 Jul 2027 | 31 Aug 2027 | Winner follow-up |
| Monitoring, Evaluation & Reporting | 15 Jul 2027 | 31 Aug 2027 | M&E report |

EDM-27-WB-1203c KTIP Challenges & Call for Solutions - Sustainable Tourism 17 - 19 May 2028 ¦ Budget: US$75,000

An open regional innovation challenge for sustainable tourism solutions. OECS Member States are acutely dependent on tourism as a primary economic driver, and the challenge is designed to surface innovations in sustainable tourism infrastructure, eco-tourism, heritage tourism, and resilient tourism business models.

- Generate implementable innovation solutions for sustainable tourism development in OECS Member States.

- Build connections between tourism innovators and the regional hospitality industry, government tourism boards, and sustainability organisations.

- Surface winning proposals eligible for grant applications through KTIP's grants discovery module.

##### Table 28: KTIP Challenges & Call for Solutions - Sustainable Tourism Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Strategic Planning & Concept Design | 2 Jul 2027 | 31 Aug 2027 | Challenge brief; prize structure |
| Governance & Coordination | 15 Aug 2027 | 31 May 2028 | Judging panel; regional tourism partners |
| Platform Integration | 15 Aug 2027 | 15 Dec 2027 | Submission workflow live |
| Partnerships & Resource Mobilisation | 1 Nov 2027 | 15 Mar 2028 |  |
| Communications & Outreach | 1 Dec 2027 | 30 Apr 2028 | Open call; regional tourism networks |
| Participant Onboarding & Capacity Building | 1 Feb 2028 | 10 May 2028 |  |
| Challenge Execution | 15 May 2028 | 19 May 2028 | Submissions close; final pitches |
| Judging & Awards | 19 May 2028 | 20 May 2028 | Prize ceremony |
| Post-Challenge Support | 21 May 2028 | 31 Aug 2028 | Winner development support |
| Monitoring, Evaluation & Reporting | 15 Mar 2027 | 30 Jun 2028 | M&E report |

EDM-27-WB-1203d KTIP Innovation Hackathon - Online 15 - 19 May 2028 ¦ Budget: US$20,000

An online collaborative innovation hackathon open to all OECS innovators, students, and entrepreneurs. The hackathon uses the KTIP Collaboration Hub - tldraw whiteboards, Tiptap documents, CodeMirror code editor, and Jitsi Meet video conferencing - as the primary collaboration infrastructure, demonstrating the platform's full capability as a remote innovation workspace.

- Drive collaborative innovation through structured team-based problem-solving using KTIP's built-in collaboration tools.

- Generate practical prototype solutions to defined OECS regional challenges.

- Build participants' skills in innovation methodology, rapid prototyping, and KTIP platform tools.

- Showcase the KTIP Collaboration Hub as a practical workspace for distributed innovation teams across the Caribbean.

##### Table 29: KTIP Innovation Hackathon – Online Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Strategic Planning & Design | 1 Jan 2028 | 29 Feb 2028 | Challenge theme; team formation rules |
| Governance & Coordination | 1 Feb 2028 | 18 May 2028 | Judging panel; prize structure |
| Platform Preparation (KTIP) | 14 Feb 2028 | 10 May 2028 | Collaboration spaces configured per team |
| Outreach & Participant Engagement | 1 Mar 2028 | 14 May 2028 | Open registration; team matching |
| Pre-Hackathon Preparation | 24 Apr 2028 | 14 May 2028 | Team briefings; mentors assigned |
| Hackathon Execution | 15 May 2028 | 18 May 2028 | 48-hour collaborative sprint |
| Prototype Development & Pitch Preparation | 15 May 2028 | 18 May 2028 | Teams build and pitch on KTIP |
| Judging & Awards | 18 May 2028 | 19 May 2028 | Prize ceremony (virtual) |
| Post-Hackathon Follow-Up | 19 May 2028 | 30 Jun 2028 | Winner development support |
| Monitoring & Evaluation | 15 May 2028 | 30 Jun 2028 | M&E report to RPIU |

EDM-27-WB-1203e KTIP Challenges & Call for Solutions - Blue Economy 12 - 14 February 2029 ¦ Budget: US$75,000

The culminating open challenge of the KTIP programme, focused on the blue economy — the OECS region's most strategically significant long-term economic frontier. By 2029, KTIP will have an established community of innovators, entrepreneurs, and industry partners built through the preceding challenges, workshops, and roadshow activities. The Blue Economy Challenge is designed to draw on this mature community to generate the most ambitious and implementable solutions of the programme.

- Generate innovation solutions for blue economy challenges: sustainable fisheries, marine conservation, coastal infrastructure resilience, ocean energy, and maritime logistics.

- Identify and support the most promising proposals for connection to regional and international blue economy funding streams.

- Produce a KTIP Blue Economy Innovation Report documenting outputs for OECS policy and development partners.

##### Table 30: KTIP Challenges & Call for Solutions - Blue Economy Activities

| Task | Start | End | Notes |
| --- | --- | --- | --- |
| Strategic Planning & Concept Design | 3 Apr 2028 | 31 May 2028 | Challenge brief; prize structure |
| Governance & Coordination | 15 May 2028 | 28 Feb 2029 | Judging panel; blue economy partners |
| Platform Integration | 15 May 2028 | 30 Sep 2028 | Submission workflow; resource packs |
| Partnerships & Resource Mobilisation | 1 Aug 2028 | 15 Dec 2028 |  |
| Communications & Outreach | 10 Sep 2028 | 25 Jan 2029 | Regional open call |
| Participant Onboarding & Capacity Building | 15 Nov 2028 | 5 Feb 2029 | Pre-submission workshops |
| Challenge Execution | 12 Feb 2029 | 14 Feb 2029 | Final pitches; judging |
| Judging & Awards | 14 Feb 2029 | 15 Feb 2029 | Prize ceremony |
| Post-Challenge Support | 15 Feb 2029 | 31 May 2029 | Winner development support |
| Monitoring, Evaluation & Reporting | 1 Dec 2028 | 31 Mar 2029 | Final M&E report to RPIU and World Bank |

### Other Innovation Initiatives

- Innovation Champion Activation (Ongoing): Quarterly virtual meetups for Innovation Champions network.

- Mentor Speed-Netowrking Events (Quarterly): Virtual matching events connecting new platform users with available mentors. Format drawn from proven models at MassChallenge and Startup Grind.

- Annual State of Ecosystem Report: Published annually on KTIP, documenting ecosystem growth, financing mobilised, new businesses created, and platform impact. Serves dual purpose of stakeholder engagement and donor reporting.

- World Innovation Day (Annually, April 21st): Flagship annual virtual event bringing together all KTIP stakeholders. Activities include annual champion recognition awards, investment forums, pitch competitions, annual launch of state of innovation in the OECS report.

# Risks & Mitigations

The following risk register draws on documented failure patterns from comparable innovation platform initiatives globally and specifically in the OECS/Caribbean context. Risks are categorised by type and rated by impact and likelihood.

##### Table 31: Risks and Mitigation Activities

| Risk | Impact | Likelihood | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- |
| Low user adoption - platform fails to attract and retain active users | High | High | Innovation Champions network ensures grassroots adoption; onboarding experience optimised for 'first value moment'; clear user journey mapping; dedicated system administrator from Day 1; monthly user experience reviews with Beta cohort | OECS TSIE + System Administrator |
| Content stagnation - insufficient fresh, high-quality content to retain returning users | High | Medium | Content calendar managed by system administrator and OECS TSIE; partner content pipelines; AI-assisted content tagging to surface relevant existing material; quarterly content audits; | OECS TSIE + System Administrator |
| Donor dependency - platform collapses when initial grant funding expires | High | Medium | Sustainability model introduced in Phase 1 (organisational memberships); diversified revenue streams targeted from Month 6; financial sustainability review at Month 9; no single donor to represent >40% of budget by Year 3 | CBU + OECS TSIE |
| Technical failure or security breach - compromising user trust | High | Low | Security-first architecture; quarterly penetration testing; incident response plan; technical team dedicated to security monitoring; | Technical Specialist EMIS and Virtual Campus + Software Development Team + RTST |
| Political disengagement - member state governments withdraw cooperation or fail to promote platform | High | Low | Governance structures include government representatives from all member states; annual government briefings by OECS Commission | OECS TSIE + RPIU |
| Connectivity barriers excluding users from smaller/less connected territories | Medium | High | Low-bandwidth mode; SMS notification option; digital literacy support via Innovation Champions; partner with telecoms providers for zero-rating KTIP access on mobile data plans | Technical Specialist EMIS and Virtual Campus + Software Development Team |
| Intellectual property disputes between platform users | Medium | Medium | Clear IP policy and Co-Creation Agreement template published before collaboration tools launch; escalation path to OECS Commission legal unit; IP legal clinic offered as platform resource | OECS TSIE + OECS Commission Legal |
| Vendor lock-in - platform becomes dependent on a single technology provider | Medium | Low | Open-source-first architecture; data portability standards built in from Day 1; multi-cloud deployment; all contracts include data export provisions; open source release planned for Year 2 | Technical Specialist EMIS and Virtual Campus |
| Platform misuse - spam, fraudulent profiles, or predatory behaviour | Medium | Medium | Mandatory identity verification for sensitive roles; community reporting tools; automated content moderation (NLP filters); clear AUP with three-strike enforcement; dedicated moderation hours daily | System Administrator |

# Success Metrics (KPIs) & Reporting

## Project Appraisal Document (PAD) Evaluation Metrics (2030)

##### Table 32: Project Evaluation Metrics

| Number of firms and entrepreneurs actively participating in KTIP (Number) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Jan/2024 | Jan/2025 | Jan/2026 | Jan/2027 | Jan/2028 | Jan/2029 | Jan/2030 |
| 0.00 | 0.00 | 100 | 200 | 300 | 400 | 400 |
| Number of innovations adopted by entrepreneurs resulting from collaboration with post-secondary education institutions (Number) |  |  |  |  |  |  |
| Jan/2024 | Jan/2025 | Jan/2026 | Jan/2027 | Jan/2028 | Jan/2029 | Jan/2030 |
| 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 2 | 4 |

## Community Growth

##### Table 33: Community Growth Metrics

| Key Indicator | Target (Year 1) | Data Source / Frequency |
| --- | --- | --- |
| New user registrations | 100 entrepreneurs/firms 300 users in total | Platform database / Monthly |
| Verified users | 25 verified mentors/investors | Platform database / Monthly |
| Active mentors | 15 active mentors | Platform database / Monthly |
| Active investors | 10 active investors | Platform database / Monthly |
| Regional distribution | 12 OECS member states | Platform database / Monthly |

## User Engagement

##### Table 34: User Engagement Metrics

| Key Indicator | Target (Year 1) | Data Source / Frequency |
| --- | --- | --- |
| Monthly active users (MAU) | ≥40% of registered users | Platform analytics / Monthly |
| Daily active users (DAU) | ≥15% of registered users | Platform analytics / Daily |
| Average session duration | ≥8 minutes | Platform analytics / Monthly |
| User retention rate | 90% of registered users | Performance analytics / Monthly |
| User satisfaction score (NPS) | NPS ≥+30 | Bi-annual user survey |

## Platform Activity

##### Table 35: Platform Activity Metrics

| Key Indicator | Target (Year 1) | Data Source / Frequency |
| --- | --- | --- |
| Active projects on platform | 50+ by Month 12 | Platform database / Monthly |
| Active mentorship relationships | 20+ by Month 12 | Mentorship module / Monthly |
| Innovation challenges completed | 2 per year | Challenge module / Quarterly |
| Challenge submissions received | 50+ per challenge | Challenge module / Per challenge |
| Projects created per month | 5 projects per month | Projects Module / Monthly |
| Forum posts and engagement | 50 posts per month | Platform forum module / Monthly |
| Events hosted | 4 events per month | Platform events module / Monthly |
| Connections made | 5+ connections per active user per month. | Platform Analytics / Monthly |

## Platform Health

##### Table 36: Platform Health Metrics

| Key Indicator | Target (Year 1) | Data Source / Frequency |
| --- | --- | --- |
| Platform uptime | ≥99.5% | Technical monitoring / Real-time |
| Average page load time | <3 seconds (3G) | Performance monitoring / Continuous |
| Security incidents (critical) | Zero critical breaches | Security audit / Quarterly |
| Support ticket resolution time | Average 24-hour resolution overall | Help desk/ticketing system / Monthly |
| Error rates | HTTP 5xx server errors below 0.5% of all requests | Platform performance monitoring tool with auto-alerts on error thresholds / Real-time alerts and monthly reports |
| User satisfaction scores | User satisfaction scores ≥4.0/5.0 | Bi-annual user survey |

## Economic Impact

##### Table 37: Economic Impact Metrics

| Key Indicator | Target (Year 1) | Data Source / Frequency |
| --- | --- | --- |
| Funding opportunities matched | 50+ users connected to funding | Partnerships Officer / Quarterly |
| Capital facilitated via KTIP | EC$1M by Month 12 | Self-reported and partner data / Annually |
| Grants awarded | 10 distinct grant awards | Funding Directory module / Quarterly and Annually. |

## Other Project Metrics

##### Table 38: Other Project Metrics

| KPI Category | Key Indicator | Target (Year 1) | Data Source / Frequency |
| --- | --- | --- | --- |
| Sustainability | Revenue from non-grant sources | 25% of operating budget by Month 12 | Financial reporting / Quarterly |
| Geographic Inclusion | Users from all 12 OECS Member States | All 12 states represented | Platform database / Monthly |
| Gender & Youth | Users under 35 | ≥60% of registered users | Platform database / Monthly |
| Gender & Youth | Gender parity in registered users | ≥45% female-identifying | Platform database / Monthly |

## Reporting Schedule

##### Table 39: Reporting Pulse

| Report | Audience & Frequency |
| --- | --- |
| Weekly Platform Pulse | Rolling KPI dashboard; community activity summary |
| Monthly Report | CBU, Technical Specialist EMIS and Virtual Campus, OECS TSIE; detailed KPI performance; user stories; risk updates, ticket summary |
| Quarterly Report | RPIU; compilation of monthly reports, impact metrics; upcoming milestones |
| Annual State of Ecosystem Report | Public; comprehensive ecosystem assessment; published on platform and distributed to all stakeholders; media distribution |
| Ad hoc Incident Reports | Technical Specialist EMIS and Virtual Campus, OECS TSIE, CBU, RPIU; issued within 24 hours of any critical security, legal, or reputational incident |

# Sustainability Plan

The KTIP is currently funded through the OECS Skills and Innovation Project (SKIP), but it is important to ensure that its utility extends well beyond the lifespan of the project. The overall goal of the sustainability plan is to ensure that at the end of the project, KTIP is able to cover its operating costs from diversified earned revenue streams. However, the sustainability plan for a regional platform such as the KTIP faces three design constraints:

- OECS Mission Constraint: KTIP is a public good serving the innovation ecosystem of a Small Island Developing State sub-region. Revenue models that extract value from users in ways that compromise accessibility e.g., paywalled core features, intrusive advertising, data monetisation, may be incompatible with the OECS Commission’s mission and will destroy user trust.

- Scale Constraint: The OECS addressable market is twelve member states with a combined population of approximately 650,000 people and a small but growing formal private sector. Revenue projections must be calibrated to this reality.

- Trust Constraint: KTIP's value depends on the quality, depth, and openness of user engagement. Any revenue mechanism that users perceive as exploitative, invasive, or misaligned with KTIP's public interest mandate will suppress engagement and ultimately destroy the platform's value, and therefore its revenue.

Therefore, the sustainability mechanisms recommended for the KTIP take these constraints into consideration and are guided by principles outlined below.

## Guiding Principles

Five (5) principles govern the design of the revenue model proposed for the KTIP:

- Free Core, Paid Premium: Individual users access all core KTIP features at no cost. Revenue is generated from organisations that derive commercial value from the platform and elect to pay for enhanced services.

- Value before Fee: No revenue stream is activated before the underlying feature or service demonstrably delivers value to paying users.

- No Third-Party Advertising: KTIP does not display third-party commercial advertising. Advertising disrupts the collaborative experience, signals commercial exploitation to users, and introduces editorial and brand integrity risks that are incompatible with a public-interest platform.

- No Monetisation of Individual Data: KTIP does not sell, license, or otherwise commercialise individual user data or identifiable behavioural data to third parties.

- Single-Source Concentration Limit: Diversification of revenue streams is a structural requirement.

It should be explicitly stated in this document that any net operating surplus generated by KTIP (revenue above operating costs) will be reinvested in the platform for feature development, community programming, and expansion to underserved territories, not distributed as profit.

## Proposed Revenue Streams

KTIP's revenue model is built on four (4) distinct revenue streams that collectively provide the diversified, resilient funding base that any single stream cannot deliver alone.

Revenue Stream 1:  Freemium Organisational Membership

Individual users access all core KTIP features free of charge. Organisations (large private companies, MSMEs, industry associations, chambers of commerce, and professional bodies) pay an annual membership fee to access premium organisational features such as: a verified, prominently featured organisation profile; advanced talent discovery tools (e.g. job board); direct challenge sponsorship options; priority listing in the KTIP partner directory.

Key Risk:  Organisations do not perceive enough value to justify renewal after first year subscription.

Risk Mitigation: Value demonstration through dedicated Quarterly Impact Report sent to each member showing: talent connections made, challenge submissions received, deals explored via the platform, and regional brand reach.

Revenue Stream 2: Innovation Challenge Sponsorship

KTIP's Innovation Challenges are the platform's highest-profile and most commercially attractive product for private sector sponsors. Sponsors pay to co-brand a challenge in their sector, early opportunity to engage with the talent behind the solutions, participate in evaluation and judging, and benefit from regional media coverage and KTIP's growing ecosystem brand. Challenge sponsorship is not advertising, it is active participation in a curated innovation programme that directly serves the sponsor's business interests by surfacing solutions to real problems they face. Sponsorship options will be tiered to provide opportunities for a wide range of stakeholders to participate.

Key Risk:  Sponsors commit to a challenge but do not see enough quality submissions to justify renewal; or the challenge market becomes saturated in a small economy.

Risk Mitigation: Strict challenge quality standards accompanied by widespread publicity of challenge details such as average submissions per challenge, geographic diversity, finalist quality, and post-challenge outcomes. Manage the number of challenges per year to maintain scarcity and quality.

Revenue Stream 3: Ecosystem Intelligence Subscription (Aggregated Data Reports)

KTIP sits at the centre of the OECS innovation ecosystem and, over time, accumulates the most comprehensive aggregated picture of innovation activity, funding flows, talent distribution, skill gaps, and sector dynamics across the sub-region. This aggregated, fully anonymised intelligence has significant commercial and policy value to development partners, multilateral organisations, national governments, research institutions, and the private sector. This intelligence can be reported as a subscription service, not individual user data, which is never commercialised, but ecosystem-level insights that no other organisation in the region can produce.

Key Risk:  Data will take some time to accumulate in order to generate rich insights; subscribers churn because insights are thin.

Risk Mitigation: This service will be delayed for a later phase to allow time for platform data to accumulate. A 6-month trial subscription will be offered to subscribers in exchange for testimonials and referrals.

Revenue Stream 4: Marketplace and Procurement Hub

As the platform reaches a critical mass of registered users and the private sector community deepens, a KTIP Innovation Marketplace, where buyers can procure locally-developed solutions, products, and services from OECS innovators, can be implemented on the platform. This will create the opportunity for a transaction-based revenue stream (small commission on verified transactions) that does not exist in the current model. This will not activated before Phase 3 because it requires critical mass to be useful and trust infrastructure that only develops over time.

Key Risk:  Trust and quality assurance failure if buyers lack confidence that listed OECS solutions are real, quality-verified, and deliverable, off-platform transaction leakage, payment infrastructure and dispute complexity.

Risk Mitigation: Launch a seller vetting process before marketplace activation. Only verified sellers list on the marketplace. Integrate an escrow-based payment layer so funds are held until the buyer confirms delivery. Partner with regional payment aggregator.

10+ Years’ experience in any field related to tech or the priority sectors or Post Graduate qualifications +7 years’ experience in any field related to tech or the priority sectors