OECS SKILLS AND INNOVATION PROJECT (SKIP)

P179210  ·  Component 1.2  ·  Education Development and Management Unit (EDMU)  ·  RPIU

KTIP Team Five-Day Launch-Readiness Sprint — Detailed Agenda Shipping the migrations, legal, and observability gaps to a launch-ready Phase 1

27 – 31 July 2026  ·  Grenada  ·  5 members

Funded by the World Bank  ·  Implemented by the OECS Commission

1.  Sprint Approach

This agenda plans the KTIP team's five days against the Consolidated Build Backlog, which reconciles the KTIP Operational Roadmap (v1.1) against the May 2026 Feature Audit. The backlog identifies thirty-five committed build features: ten are built to Phase 1 intent, nine are partial and need extension, and sixteen are absent. The absent items are the strategically important ones — the trust and IP infrastructure, the mentorship engine, the AI matchmaking engine, and the investor, marketplace and blockchain surfaces — and the roadmap itself places them in the Months 3–6 and 6–12 windows.

This sprint is therefore not an attempt to build the whole platform. Its single objective is to make a credible Phase 1 subset launch-ready for the hard 10 August 2026 date. That means completing the two unshipped migration sets, finishing the partial Phase 1 modules, and standing up the legal, observability and pipeline layer that the roadmap's own targets and pre-registration requirements depend on. The trust infrastructure, mentorship, AI matchmaking, investor, marketplace and blockchain commitments are explicitly deferred to their roadmap windows and are out of scope for these five days.

KTIP runs on a SolidJS 1.9 + Tailwind v4 + Supabase stack (per the audit of the actual repository, not the roadmap's templated React description), and the correction of that stack description in the roadmap is one of the first-day reconciliation tasks.

Priority key

| Launch gate | P0 — launch-blocking | P1 — as capacity allows | Deferred to Months 3–12: trust/IP infrastructure, blockchain IP registry, mentorship, AI matchmaking, investor & marketplace surfaces |
| --- | --- | --- | --- |

A note on the three reconciliations: before build planning, the backlog flags three conflicts to resolve on Day 1 — correct the stack description to SolidJS; treat the audit's “broken” Proposals and Documents features as unshipped roadmap commitments to complete, not defects to delete; and confirm that the blockchain IP registry and Badges are committed (Badges is a Phase 1 module; blockchain is deferred with a design-decision gate). These are Marvin's first-day items.

2.  Track Ownership

The five members hold the launch-readiness workstreams according to their roles. Marvin (KTIP Lead, Plan/Roadmap) coordinates, resolves the three reconciliations, and owns the launch-scope and gate. Dean (Database) ships the missing migrations — the single most important first action — and the database work behind the partial modules. Philan (Software, System Integration) stands up the CI/CD pipeline, observability and alerting, and reconciles the third-party integration paths. Delon (Software Engineer, AI Integration) completes the partial Phase 1 modules (Projects/Collaboration Hub, Challenges, Notifications email, RBAC extension). Johnique (Software and Implementation) delivers the legal and compliance layer, data export/deletion, and accessibility conformance. The launch-blocking infrastructure and legal work is treated as P0 alongside the migrations, because the roadmap's own 10 August date depends on it.

| Member | Role / focus | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 |
| --- | --- | --- | --- | --- | --- | --- |
| Marvin | KTIP Lead — coord, roadmap, scope | Reconciliations + scope freeze | Stack + video-path decisions | Integration checkpoint | Launch-scope comms | Launch-gate review |
| Dean | Database — migrations | Ship proposals/documents migs | Verify + seed reference data | Module DB support | RBAC matrix + export schema | Migration integrity proof |
| Philan | System Integration — CI/CD + obs. | CI/CD pipeline (GitHub Actions) | Error tracking + alerting | Load/scale test harness | Email (Sendgrid) + video path | Launch-gate infra proof |
| Delon | SW Eng — partial Phase 1 modules | Projects/Collab Hub completion | Challenges (proposals wired) | Notifications email + prefs | RBAC extension + flagging | Module QA + demo |
| Johnique | SW & Impl — legal/compliance | Legal pages scaffold | Privacy/Terms/AUP + cookie | Data export + self-delete | Accessibility (axe-core) + AUP | Compliance sign-off |

The Day 1 prerequisites (staging environment, migration runner, error tracking, seed data, scope freeze, and the three reconciliations) are a whole-team first-half-day; the allocation above shows each member's primary thread once the prerequisites are in place.

KTIP Team Members

The KTIP launch-readiness build is delivered by the following members of the OECS Software Development Team. Assignments are indicative and confirmed at the Day 1 scope freeze.

| # | Member | Role / focus | Originating Country |
| --- | --- | --- | --- |
| 1 | Marvin Pacheco | KTIP Lead — planning, roadmap, launch scope | Trinidad and Tobago |
| 2 | Dean Kayode Vidal | Database — migrations and schema | Dominica |
| 3 | Philan James | Software, system integration — CI/CD, observability | Saint Lucia (NSDC) |
| 4 | Delon Pierre | Software engineer, AI integration — Phase 1 modules | Saint Lucia |
| 5 | Johnique Williams | Software and implementation — legal & compliance | Saint Kitts and Nevis |

3.  Day-by-Day Agenda

Day 1 (27 July) — Prerequisites, Reconciliations, and Migration Ship

The morning stands up the launch-gate prerequisites and resolves the three reconciliations. The afternoon starts the single most important build action — shipping the missing migrations — alongside the CI/CD and legal-page groundwork.

| Time | Block | Focus |
| --- | --- | --- |
| 08:30 | Stand-up + scope freeze | Whole team. Freeze the launch-blocking Phase 1 subset; assign tracks; set the Day 3 integration checkpoint and Day 5 launch-gate review. |
| 09:00 | Three reconciliations (Marvin) | Correct the stack to SolidJS 1.9 + Tailwind v4 + Supabase; confirm Proposals and Documents are unshipped roadmap features to complete (not defects to delete); confirm Badges committed (Phase 1) and blockchain deferred with a design-decision gate. |
| 10:00 | Prerequisites | Whole team. Staging environment; migration runner that applies migrations in order and verifies; Sentry-equivalent error tracking; seed data. |
| 12:30 | Lunch |  |
| 13:30 | Ship migrations (Dean) | Ship the proposals, documents and document_shares migration sets — the backlog's first recommended action — restoring the Proposals module and the Collaboration Hub document tooling that challenges and hackathons depend on. |
| 13:30 | CI/CD + legal kick-off | Philan begins the GitHub Actions CI/CD pipeline; Johnique scaffolds the legal pages (/privacy, /terms, /cookie, AUP); Delon begins the Projects/Collaboration Hub completion against the new migrations. |
| 16:30 | Day 1 checkpoint | Confirm gates live: staging, migration runner, error tracking, seed data; migrations applied cleanly; reconciliations recorded. Any gate not met is the first order of Day 2. |
| 17:00 | Close |  |

Day 2 (28 July) — Partial Modules, Observability, Legal Content

The first full build day. Migrations are verified and seeded; the partial Phase 1 modules advance; observability and the legal content go in.

| Time | Block | Focus |
| --- | --- | --- |
| 08:30 | Stand-up | Per-track goals; surface cross-track dependencies (migrations feed the modules; RBAC feeds legal access rules). |
| 09:00 | Dean — verify + seed | Verify the shipped migrations against the runner; seed the 50+ resources and reference data the modules need; confirm no orphaned tables remain. |
| 09:00 | Delon — Challenges (proposals wired) | Wire the Challenges & Open Innovation engine through the now-shipped proposals table; confirm submissions flow end to end. |
| 09:00 | Philan — error tracking + alerting | Stand up error tracking, a status page, and 5xx auto-alerts (roadmap §9.4), so the Platform Health KPIs become measurable. |
| 09:00 | Johnique — Privacy/Terms/AUP + cookie | Draft privacy policy, terms of use with the full IP obligations (Table 13), cookie consent, and the Acceptable Use Policy; route for legal review. |
| 12:30 | Lunch |  |
| 13:30 | Marvin — stack + video-path decisions | Record the corrected stack in the roadmap; reconcile the conflicting video specs (Jitsi self-host vs Zoom/Google Meet integration) to a single primary path before mentorship/hackathon scheduling. |
| 15:15 | Module + infra advance | Delon continues Projects/Collab Hub; Philan begins the load/scale test harness; Dean supports module DB needs. |
| 16:45 | Daily output log | Progress recorded per track; blockers raised for Day 3. |
| 17:00 | Close |  |

Day 3 (29 July) — Completion and Integration Checkpoint

P0 items are driven toward completion. A mid-afternoon integration checkpoint reconciles the migrations, modules, legal access rules and pipeline before the final push.

| Time | Block | Focus |
| --- | --- | --- |
| 08:30 | Stand-up | Confirm which P0 items are closeable today; flag any at risk for the checkpoint. |
| 09:00 | Delon — Notifications email + prefs | Complete the Notification System: add the email channel (roadmap requires push AND email) and the preferences/settings page. |
| 09:00 | Philan — load/scale test | Run the first load/scale test against the roadmap targets (99.5% uptime, <3s load on 3G, <0.5% 5xx); capture baselines. |
| 09:00 | Johnique — data export + self-delete | Build self-service data export (open format) and account self-deletion (GDPR Art. 15/17; roadmap requires deletion at any time). |
| 09:00 | Dean — module DB support | Support the modules' remaining schema needs; confirm RBAC and notification-preferences tables. |
| 12:30 | Lunch |  |
| 14:00 | Integration checkpoint | Whole team. Reconcile migrations, modules, legal access rules, pipeline and observability. Confirm the P0 status honestly and re-cut the P1 list for Days 4–5. Marvin confirms the launch scope. |
| 15:15 | P0 close-out | Each track closes remaining P0 items or routes them into the post-session plan with a named owner. |
| 16:45 | Daily output log | P0 status recorded; Day 4–5 P1 scope confirmed. |
| 17:00 | Close |  |

Day 4 (30 July) — Extensions, Integrations, and Compliance Close

With the core P0 substantially closed, the day takes the highest-value extensions (RBAC matrix, content flagging), the email/video integrations, and the accessibility and AUP close-out.

| Time | Block | Focus |
| --- | --- | --- |
| 08:30 | Stand-up | Confirm the P1 items each track will complete; anything not started today is deferred cleanly to the post-session plan. |
| 09:00 | Dean — RBAC matrix + export schema | Build the configurable per-role access matrix (richer than the current binary owner/admin model) approved by the Technical Specialist; finalise the export schema. |
| 09:00 | Delon — RBAC extension + content flagging | Extend RBAC in the app against Dean's matrix; add 24-hour-review content flagging across projects, resources and forums. |
| 09:00 | Philan — email + video path | Wire Sendgrid/Mailchimp to deliver the email half of the Notification System; implement the single chosen video path (from Day 2 decision). |
| 09:00 | Johnique — accessibility + AUP | Run the axe-core accessibility audit toward WCAG 2.1 AA; finalise the Acceptable Use Policy and confirm all legal pages deploy before registration. |
| 12:30 | Lunch |  |
| 13:30 | Marvin — launch-scope comms | Draft the launch-scope statement: a credible Phase 1 subset, with the trust/mentorship/AI and investor/marketplace/blockchain items sequenced into Months 3–12 per the roadmap's Now/Next/After structure. |
| 15:15 | CI verification | Philan wires the test suites into CI on every pull request; confirm the release process runs migrations verified in the pipeline. |
| 16:45 | Daily output log | P1 progress recorded; items for Day 5 confirmed. |
| 17:00 | Close |  |

Day 5 (31 July) — Launch-Gate Review and Close

The morning completes verification and the compliance sign-off. The afternoon is the whole-team launch-gate review against the definition of done, followed by the session close.

| Time | Block | Focus |
| --- | --- | --- |
| 08:30 | Stand-up | Confirm what must land before the launch-gate review; freeze new work. |
| 09:00 | Dean — migration integrity proof | Prove all migrations apply cleanly via the runner on a fresh database; no orphaned tables; reference data seeded. |
| 09:00 | Philan — infra proof | Confirm CI/CD green, error tracking live with a triggered alert visible, load test within targets. |
| 09:00 | Johnique — compliance sign-off | Confirm privacy, terms, cookie consent and AUP are deployed and gate registration; data export and self-delete work; accessibility findings triaged. |
| 09:00 | Delon — module QA + demo | Demo the completed Phase 1 modules end to end on staging: Projects/Collab Hub, Challenges, Notifications (push + email). |
| 12:30 | Lunch |  |
| 13:30 | Launch-gate review | Whole team, against the definition of done: migrations applied cleanly; Phase 1 subset complete and demoed on staging; legal pages deployed and gating registration; observability and alerting live; CI/CD green; load test within targets; deferred scope documented with owners. |
| 15:15 | Post-session work plan | Route the deferred trust/IP, mentorship, AI matchmaking, investor, marketplace and blockchain items into the Months 3–12 plan with named owners and the blockchain design-decision gate. |
| 16:15 | Docs + formal close | Update the roadmap (corrected stack, launch scope), the migration and deployment runbook, and the compliance record. RPIU close; next engagement confirmed. |
| 17:00 | Session close |  |

4.  Launch-Gate Definition of Done (Day 5 Review)

The sprint is judged against the following gate, aligned to the 10 August 2026 launch. Any item not met is routed into the post-session work plan with a named owner.

- The proposals, documents and document_shares migrations are shipped and apply cleanly via the runner on a fresh database, with no orphaned tables.

- The launch Phase 1 subset is complete and demoed on staging: profiles, discovery, grants, events, resources, and a completed Projects/Collaboration Hub, plus Challenges wired through Proposals.

- The Notification System delivers both push and email, with a preferences page.

- Legal pages — privacy policy, terms of use with the full IP obligations, cookie consent, and the AUP — are deployed and gate user registration.

- Self-service data export and account self-deletion work (GDPR Art. 15/17).

- Error tracking, a status page and 5xx alerting are live; a deliberately triggered error appears in the dashboard.

- The CI/CD pipeline runs the tests and applies migrations verified in the pipeline on every release.

- A load/scale test has been run against the roadmap targets and results recorded.

- Accessibility findings from the axe-core audit are triaged toward WCAG 2.1 AA.

- The three reconciliations are recorded, the roadmap stack description is corrected, and the launch scope is stated as a credible Phase 1 subset.

- The deferred trust/IP, mentorship, AI matchmaking, investor, marketplace and blockchain items are documented in the Months 3–12 plan, with the blockchain design-decision gate named.

5.  Deferred Scope and External Dependencies

Deferred to the roadmap's Months 3–12 windows

Blockchain-based IP registry (with a mandatory design-decision gate on chain, cost model and what is anchored vs hashed), rights-clearance checklist, confidentiality marking, AI content-disclosure form, automated NLP spam/harmful-content filters, the six-stage takedown workflow, the Mentorship Programme Manager, the AI Discovery & Matchmaking engine, the Investor Deal Flow Portal and weekly investor digest, the Marketplace & Procurement Hub, and the LMS integration with the Virtual Campus. These carry named owners in the post-session plan and sit in the roadmap's own Now/Next/After sequencing.

Cross-track and external dependencies

- Legal review of the privacy policy, terms of use, cookie policy and AUP — required before registration opens; the drafting is in-sprint but the sign-off is an organisational/legal dependency.

- The video-conferencing path (Jitsi vs Zoom/Google Meet) must be decided before mentorship and hackathon features are scheduled — both depend on it.

- The blockchain IP registry needs a dedicated design decision before any build commitment — it is the largest unspecified engineering item and the most exposed technical risk.

- The LMS integration ties to the Virtual Campus sprint — a cross-platform dependency on that team.

6.  Glossary of Technical Terms

This glossary explains the technical terms and abbreviations used in the agenda above, for readers who are not software specialists. It is grouped into sprint and process terms, and platform and engineering terms.

Sprint and process terms

| Term | Full name | In plain terms |
| --- | --- | --- |
| Sprint | — | A short, focused block of development work with a fixed goal — here, the five days in Grenada. |
| Backlog | — | The full list of outstanding work items still to be tackled; here the reconciled KTIP build register of 35 features. |
| Roadmap | — | The plan describing the intended platform and its delivery phases (KTIP Operational Roadmap v1.1). |
| Feature audit | — | A review of what the code actually contains, as opposed to what the roadmap intended (May 2026). |
| Reconciliation | — | Resolving a disagreement between the roadmap and the audit into a single agreed action. |
| Phase 1 / 2 / 3 | — | The roadmap's delivery windows: Phase 1 (Months 0–3, launch), Phase 2 (3–6), Phase 3 (6–12). |
| P0 / P1 | Priority 0 / 1 | P0 must be done and blocks launch; P1 is important and taken as capacity allows. |
| Launch gate | — | A must-pass condition before the platform can go live on 10 August. |
| Definition of done | — | The agreed checklist that decides when the work is genuinely finished. |
| Scope freeze | — | Fixing exactly what will and will not be attempted, so the plan does not grow mid-sprint. |
| Present / Partial / Absent | — | The audit's status for each feature: fully built, part-built, or not built. |
| Net-new | — | A feature that does not exist yet and must be built from scratch. |

Platform and engineering terms

| Term | Full name | In plain terms |
| --- | --- | --- |
| Migration | — | A controlled, ordered change to the database structure. The KTIP gap is that some UIs reference tables whose migrations were never shipped. |
| Proposals / Documents tables | — | Database tables the Proposals module and Collaboration Hub need; their migrations are missing, so those features break at runtime. |
| Collaboration Hub | — | The KTIP workspace for shared documents, whiteboards, code and video used in projects and hackathons. |
| Migration runner | — | A tool that applies database migrations in the correct order and verifies they succeeded. |
| Staging environment | — | A private copy of the platform that mirrors the live one, used to test safely before launch. |
| Seed data | — | Initial reference content loaded into the platform (for example the 50+ resources the library needs). |
| CRUD | Create, Read, Update, Delete | The basic operations on a record; “Project CRUD present” means projects can be created, viewed, edited and deleted. |
| RBAC | Role-Based Access Control | Controlling what each user can do based on their role; the roadmap wants a configurable per-role access matrix. |
| Access matrix | — | A table setting out exactly which role may do what, richer than a simple owner/admin split. |
| RLS | Row-Level Security | A database safeguard controlling which specific records each user can see. |
| Notification System | — | How the platform tells users about activity; the roadmap requires both in-app (push) and email channels. |
| Push / email channel | — | The two ways notifications reach users: in-app alerts, and email delivered via a service like Sendgrid. |
| CI/CD | Continuous Integration / Continuous Delivery | An automated pipeline that runs tests and applies database migrations on every code change and release. |
| GitHub Actions | — | The tool used to build that CI/CD pipeline. |
| Observability | — | Being able to see what the platform is doing, through dashboards, logs and a status page. |
| APM | Application Performance Monitoring | Tooling (e.g. Datadog) that watches the live platform's health around the clock. |
| Alerting | — | Automatic notifications when something goes wrong (for example a 5xx server-error spike). |
| 5xx | — | Server-side error responses; a low 5xx rate is one of the roadmap's health targets. |
| Load / scale testing | — | Testing how the platform behaves under many simultaneous users, against uptime and speed targets. |
| 99.5% uptime / <3s on 3G | — | Roadmap health targets: available almost all the time, and pages loading within three seconds on a 3G connection. |
| Legal pages | — | Privacy policy, terms of use, cookie consent and Acceptable Use Policy — required before user registration opens. |
| AUP | Acceptable Use Policy | The rules users agree to about how they may use the platform. |
| Data portability / export | — | Letting users take their data out in an open format, and delete their account (GDPR Articles 15 and 17). |
| GDPR Art. 15/17 | General Data Protection Regulation | The data-protection rights to access your data (15) and to have it erased (17). |
| Accessibility (a11y) / WCAG 2.1 AA | Web Content Accessibility Guidelines | Designing so people with disabilities can use the platform, measured against an international standard. |
| axe-core | — | The tool used to audit the platform for accessibility issues. |
| Blockchain IP registry | — | A proposed trust feature recording intellectual-property ownership on a blockchain; deferred pending a design decision. |
| Anchored vs hashed | — | Two ways to record data on a blockchain: storing a full record (anchored) versus storing only a fingerprint of it (hashed) — a key cost/design choice. |
| Rights-clearance checklist | — | A prompt at upload confirming the uploader owns the content and its licence — part of the IP protection layer. |
| Confidentiality marking | — | Labelling content Confidential / Restricted / Internal / Public / Draft with access enforced by the system. |
| NLP filters | Natural Language Processing | Automated tools that scan text to flag spam or harmful content, rather than relying only on manual reports. |
| Matchmaking engine | — | The AI feature that recommends relevant projects, people or opportunities to users; a deferred net-new build. |
| SolidJS / Tailwind / Supabase | — | The technologies KTIP is actually built on (front-end framework, styling, and backend) — the audit corrected the roadmap's description of these. |
| tldraw / TipTap / CodeMirror / Jitsi | — | The specific tools for whiteboards, document editing, code editing and video in the Collaboration Hub. |
| Sanitisation | — | Cleaning user-entered content so it cannot carry a security attack (such as cross-site scripting). |

This agenda is a working plan for the KTIP team and will be adjusted at the Day 1 scope freeze and the Day 3 integration checkpoint against actual progress.